Investment Readiness & Investment Round Management

Proposal and Consulting Agreement

| Prepared for | Btakka — [Insert Registered Legal Entity Name] |
| --- | --- |
| Prepared by | Abdelrhman Soliman — Investment & Business Expert |
| Date | 13 September 2026 |
| Validity of this proposal | 30 days from the date above |

Document Control

| Field | Detail |
| --- | --- |
| Document title | Investment Readiness & Investment Round Management — Proposal and Consulting Agreement |
| Version | 1.0 — For Client Review |
| Consultant | Abdelrhman Soliman, Independent Investment Advisor & Consultant |
| Consultant address | Cairo, Arab Republic of Egypt |
| Consultant contact | abdelrhmansoliman96@gmail.com · +20 109 651 5287 |
| Client (trade name) | Btakka |
| Client (legal entity) | [Insert full registered name] |
| Commercial Register No. | [Insert CR number] |
| Tax Card No. | [Insert tax ID] |
| Registered address | [Insert address] |
| Client signatory | [Insert name and title] |
| Target round | Pre-Seed |
| Total engagement fee | EGP 150,000 plus a 10% Success Fee on Consultant-introduced tickets |
| Indicative duration | 4 months (1 month readiness + 3 months round management) |

How to read this document. Part I — Proposal sets out what will be done, by whom, by when, and for how much. Part II — Consulting Agreement is the binding contract. Part III — Schedules contains the detailed scope, workshop programme, input requirements, fee schedule and investor log that the Agreement incorporates by reference. Fields shown as [ ] are to be completed before signature.

PART I — PROPOSAL

1. Executive Summary

Btakka operates two published iOS products on the Egyptian App Store — Btakka Business (App Store) and Btakka Finishing & Decor (App Store). A live product in market is the hardest part of a pre-seed story, and Btakka already has it.

What most pre-seed companies in this position lack is not a product and not ambition — it is the evidence package. Investors do not fund a good idea described well. They fund a company that can answer every question in a diligence checklist within twenty-four hours, with numbers that reconcile, a story that holds under pressure, and a founder who has clearly done this work before the meeting rather than during it.

This engagement delivers exactly that, in two phases:

Phase 1 — Investment Readiness (1 month). Build the complete pre-seed data room against the 36-item checklist, the financial model and financial expectations, the valuation, the pitch deck, the teaser, the business plan and the full investor document set. Delivered through four structured workshops that transfer the reasoning to the founding team, not just the files.

Phase 2 — Investment Round Management (3 months). Convert readiness into capital: fundraising strategy, investor target map, structured outreach, meeting management, diligence coordination, term sheet negotiation and close.

Commercials. EGP 150,000 in fixed fees across three milestones (EGP 30,000 on signature, EGP 30,000 on completion of readiness, EGP 90,000 on first close), plus a 10% Success Fee on the value of investment tickets funded by investors the Consultant introduced.

The one thing that determines whether this works. Every deadline in this document is conditional on Btakka's engagement — documents delivered on time, workshops attended by decision-makers, and introduced investors answered within three business days. This is stated plainly in Clause 5 and Clause 7 because it is the single largest cause of failed rounds, and it is the one input the Consultant cannot supply.

2. About the Consultant

Abdelrhman Soliman is an independent investment advisor based in Cairo, working with founders, angels, VCs and family offices across MENA and global markets. Specialisations: investment evaluation, fundraising strategy, investor relations, financial modelling and portfolio development.

Track record

| Metric | Figure |
| --- | --- |
| Years in VC, PE and advisory | 7+ |
| Startups mentored | 100+ |
| Capital raised supported | USD 10M+ |
| Financial models built and reviewed | 50+ |
| Peak simulated fund DPI | 120x |

Experience

| Period | Role | Organisation |
| --- | --- | --- |
| Jun 2026 — present | Independent Investment Advisor & Consultant | Private Practice |
| 2025 — 2026 | Syndicate Lead & Head of Investment | Multiples Ventures |
| 2024 — 2025 | Senior Investment Analyst | Multiples Ventures |
| 2024 — present | Startup Investment Mentor | Startupbootcamp · VC4A |
| 2022 — 2023 | Investment Unit Supervisor | G. World MENA |
| 2020 — 2022 | Investment Analyst | G. World MENA |

Recognition

Top 4% — VC Lab, Cohort 17. Among the top 4% of emerging fund managers globally; validated a USD 3M pre-seed SaaS fund thesis.

Winner — Fintech Saudi 2024 Content Challenge, for "Reimagining the Financial Services Value Chain".

Top 10 LinkedIn VC Creators, MENA, for thought leadership and founder education.

+120x simulated growth-stage DPI and +6x early-stage DPI, VC Fund Manager Masterclass.

Credentials

CFA Level I (CFA Institute) · VC & Private Equity (Bocconi) · Advanced Valuation (Erasmus Rotterdam) · Investment Banking virtual experience (J.P. Morgan) · Alternative Investing (Apollo Academy) · Data Analysis (Dubai Future Foundation).

Sectors covered

SaaS · Fintech · E-commerce · Real Estate · Ed-tech · Logistics · Climate Tech · Retail.

Speaking and media

Startupbootcamp · VC4A · Startup Without Borders · TINTS Business Lobby · Asharq News (Sharq Bounce) · Alhadath Alyoum TV (Financial Market) · Investment World LinkedIn newsletter · YouTube founder-education channel.

3. Understanding of Btakka

The Consultant's present understanding is based on the two publicly listed applications and the materials shared to date. It will be confirmed, corrected and completed in the Discovery & Story Workshop (W1), which is scheduled as the first substantive session of the engagement precisely so that no downstream deliverable is built on an assumption.

| What is established | What will be established in W1 |
| --- | --- |
| Two live iOS products published on the Egyptian App Store | Current traction: downloads, activations, active users, retention |
| A B2B/business-facing product (Btakka Business) | Revenue model in force today and monetisation actually collected |
| A vertical product for finishing and décor | Unit economics: CAC, payback, contribution margin, LTV |
| The company is at pre-seed stage and raising | Target round size, instrument, valuation expectation and use of funds |
| A founding team is in place | Cap table, prior funding, founder vesting, current runway and burn |
| A product roadmap exists | Competitive set, defensibility and the wedge into the market |

Why this matters. A pre-seed investor in Egypt is underwriting three things: that the market is large enough, that this team can execute, and that the money buys a specific, measurable step-change. The data room is the instrument that proves all three. Everything in Phase 1 is built to answer those three questions and nothing else.

4. Engagement Objective

To take Btakka from its current position to a funded pre-seed round, by:

Producing an investor-grade data room covering all 36 items of the Pre-Seed Round Data Room Checklist.

Producing a defensible financial model, financial expectations and valuation that withstand investor scrutiny.

Producing the complete investor document set — pitch deck, teaser, business plan, term sheet template and valuation.

Equipping the founding team, through workshops, to own and defend every number and every claim.

Running a structured, time-boxed fundraising process from strategy through outreach to signed close.

What "success" means in this document. Phase 1 succeeds when the data room passes a diligence readiness review and is signed off (Schedule A). Phase 2 succeeds when investment funds are received in cleared funds in Btakka's account. The Consultant does not, and cannot, guarantee that a round will be funded — see Clause 12.

5. Scope of Work

Phase 1 — Investment Readiness (Weeks 1–4)

Workstream A — Story, Positioning & Market

Investment thesis and narrative spine for Btakka

Problem/solution framing calibrated to pre-seed investor expectations

Market sizing: TAM, SAM and SOM with sourced, defensible methodology

Competitive analysis and differentiation map

Go-to-market strategy and customer acquisition plan

Customer development evidence pack and traction narrative

Workstream B — Financial Model, Expectations & Valuation

Full driver-based financial model, 3–5 year horizon, monthly for year 1–2

Revenue model across both product lines, built on real unit economics

Cost structure: COGS, operating expenses, and headcount costs derived from Btakka's HR plan

Cash flow, burn rate, runway and current cash position statement

Base / conservative / upside scenarios with sensitivity analysis

Financial expectations pack — the forward projections investors will underwrite

Use of Funds statement covering a 12–18 month runway with milestone mapping

Pre-seed valuation with method, comparables and a defensible range

Current and post-money cap table, including dilution scenarios

Key metrics dashboard and operational KPI set

Workstream C — Data Room Construction

Full data room architecture, folder structure, naming convention and index

Preparation, drafting or investor-formatting of every Consultant-owned item in Schedule A

Collection, review and quality control of every Client-provided item in Schedule A

Gap analysis and a remediation list for anything missing, weak or inconsistent

Diligence Q&A bank — the questions investors will ask, with prepared answers

Access control, permissioning and version discipline

Final diligence readiness review and sign-off

Workstream D — Investor Document Set

Pitch deck — 10–15 slides: problem, solution, market, product, traction, business model, competition, team, financials, the ask

Teaser — one-page designed summary for first-touch outreach

Business plan — full narrative document, all parts

Term sheet template — proposed investment terms reflecting Btakka's valuation expectations

Valuation document — method, assumptions, comparables and conclusion

Founder bios written to investor standard, from the CVs provided

Product demo script and walkthrough structure built around the app screenshots provided

Phase 2 — Investment Round Management (Months 2–4)

Stage 1 — Fundraising Strategy (Weeks 5–6)

Round architecture: size, instrument (equity / SAFE / convertible note), valuation and terms

Investor segmentation: angels, syndicates, pre-seed funds, family offices, strategic and corporate investors, accelerators and relevant Egyptian and regional programmes

Target Investor Map with prioritised tiers, thesis fit and warm-path mapping

Outreach infrastructure: sequencing, messaging, channel plan and tracking

Pitch rehearsal and objection handling with the founding team

Round timeline with weekly milestones and a defined close target

Stage 2 — Outreach & Investor Engagement (Weeks 7–12)

Structured outreach waves against the Target Investor Map

Warm introductions through the Consultant's network where available

Teaser and deck distribution under version and access control

Meeting scheduling, preparation briefs and post-meeting debriefs

Investor feedback captured, analysed and fed back into the materials

Weekly pipeline reporting: contacted, engaged, in diligence, term sheet, closed

Iteration of deck, model and data room in response to real investor objections

Stage 3 — Diligence, Negotiation & Close (Weeks 13–16)

Diligence management: request coordination, response drafting, data room administration

Investor question handling and escalation

Term sheet review, commercial commentary and negotiation support

Valuation and dilution modelling across competing offers

Syndicate construction where multiple investors participate

Coordination with Btakka's legal counsel through to signing and funding

Post-close investor reporting structure and investor update template

6. Workshop Programme

Workshops are the mechanism by which the reasoning behind every deliverable is transferred to the founding team. A founder who cannot defend their own model in a meeting does not get funded, regardless of how good the model is.

| # | Workshop | Timing | Duration | Required attendees | Output |
| --- | --- | --- | --- | --- | --- |
| W1 | Discovery & Story Session — initial meeting to understand the story | Week 1 | 3 hours | All founders | Confirmed business understanding, investment thesis draft, full information request list |
| W2 | Financial Modelling Workshop — Session 1 | Week 2 | 3 hours | Founders + finance lead | Driver tree, unit economics, assumption book v1 |
| W3 | Financial Modelling Workshop — Session 2 | Week 3 | 3 hours | Founders + finance lead | Model review and challenge, scenarios, use of funds, valuation range |
| W4 | Full Data Room Workshop | Week 4 | 4 hours | Full leadership team | Complete data room walkthrough, diligence Q&A drill, readiness sign-off |
| W5 | Investor Pitch Rehearsal | Week 5 | 2 hours | Pitching founders | Pitch calibration, objection handling, go-live sign-off |

All workshops may be held in person in Cairo or remotely by video, at Btakka's preference. Sessions are recorded and a written summary with action items is issued within two business days. Full detail is at Schedule B.

7. Deliverables

Every deliverable below is produced by the Consultant and handed over in both editable source format and a final PDF, except where noted.

Phase 1 deliverables

| # | Deliverable | Format | Due by |
| --- | --- | --- | --- |
| 1 | Data room architecture and index | Folder structure + index sheet | Week 1 |
| 2 | Information request list and gap analysis | Tracker | Week 1 |
| 3 | Investment thesis and narrative spine | Document | Week 2 |
| 4 | Market sizing — TAM / SAM / SOM | Document + model | Week 2 |
| 5 | Competitive analysis | Document | Week 2 |
| 6 | Financial model (driver-based, 3–5 years) | Excel | Week 3 |
| 7 | Financial expectations pack | Excel + document | Week 3 |
| 8 | Revenue model overview | Document | Week 3 |
| 9 | Scenario and sensitivity analysis | Excel | Week 3 |
| 10 | Use of Funds statement | Document | Week 3 |
| 11 | Cap table (current and post-money) | Excel | Week 3 |
| 12 | Valuation document | Document + model | Week 3 |
| 13 | Key metrics dashboard | Excel | Week 3 |
| 14 | Go-to-market strategy | Document | Week 3 |
| 15 | Pitch deck (10–15 slides) | Designed deck + source | Week 4 |
| 16 | Teaser (one page, designed) | Designed PDF + source | Week 4 |
| 17 | Business plan (all parts) | Document | Week 4 |
| 18 | Term sheet template | Document | Week 4 |
| 19 | Founder bios (investor standard) | Document | Week 4 |
| 20 | Product demo script and walkthrough | Document | Week 4 |
| 21 | Technical overview | Document | Week 4 |
| 22 | Organisational chart and key hire plan | Document | Week 4 |
| 23 | Diligence Q&A bank | Document | Week 4 |
| 24 | Complete, indexed, populated data room | Live data room | Week 4 |
| 25 | Diligence readiness review and sign-off | Report | Week 4 |

Phase 2 deliverables

| # | Deliverable | Format | Due by |
| --- | --- | --- | --- |
| 26 | Fundraising strategy document | Document | Week 6 |
| 27 | Round architecture and terms recommendation | Document | Week 6 |
| 28 | Target Investor Map (tiered, with warm paths) | Tracker | Week 6 |
| 29 | Outreach plan, sequences and messaging | Document | Week 6 |
| 30 | Investor Log (maintained live) | Tracker | Weekly from Week 7 |
| 31 | Weekly pipeline report | Report | Every week, Weeks 7–16 |
| 32 | Meeting preparation briefs and debriefs | Documents | Per meeting |
| 33 | Investor feedback analysis and materials iteration | Report + updated materials | Rolling |
| 34 | Diligence response coordination pack | Documents | As required |
| 35 | Term sheet review and negotiation commentary | Document | On receipt |
| 36 | Dilution and offer comparison model | Excel | On receipt |
| 37 | Investor update template and reporting structure | Template | At close |
| 38 | Engagement closing report and handover | Report | At close |

8. What Btakka Must Provide

The engagement cannot start without the Client Input Pack. These seven items are required within five business days of signature, and the Phase 1 clock starts on the date the last of them is received.

| # | Item | What is needed | Format |
| --- | --- | --- | --- |
| 1 | Company profile | Company overview, history, milestones, legal structure, what Btakka does in the founders' own words | Document |
| 2 | HR plan | Current headcount by role, current salary cost, planned hires with roles, timing and cost | Excel or document |
| 3 | Product roadmap | 6–12 month development plan with milestones for both applications | Document or board export |
| 4 | App screenshots | High-resolution screenshots of both applications covering the core user journeys | PNG or JPG, high resolution |
| 5 | Founding team CVs and photos | Full CV for each founder and key team member, plus a professional photograph of each | PDF + image files |
| 6 | Brand guidelines | Logo files, colour palette, typography, and any existing brand or design system | Brand book + vector logo files |
| 7 | Business model | How Btakka makes money today and intends to, across both product lines, with pricing | Document |

In addition, the items marked Client in Schedule A are required — principally the legal and corporate documents, historic financial statements, bank balances, traction data and customer evidence. The Consultant will issue a single consolidated request list at Workshop W1 so that nothing is requested twice.

Btakka must also provide: a single named point of contact empowered to make decisions; founder availability for the five workshops; responses to information requests within five business days; and responses to introduced investors within three business days (Clause 5).

9. Timeline

Phase 1 — Investment Readiness: 4 weeks

| Week | Focus | Workshop | Milestone |
| --- | --- | --- | --- |
| Week 0 | Signature, deposit, NDA, Client Input Pack request, data room provisioning | — | Engagement mobilised |
| Week 1 | Discovery, business deep dive, information collection, data room architecture | W1 | Information request issued; data room structure live |
| Week 2 | Market sizing, competitive analysis, thesis, model build begins | W2 | Assumption book agreed; market pack delivered |
| Week 3 | Model completion, scenarios, use of funds, valuation, cap table | W3 | Financial model, expectations and valuation delivered |
| Week 4 | Investor document set, data room population, readiness review | W4 | Phase 1 complete — data room signed off |

Phase 2 — Investment Round Management: 3 months

| Period | Focus | Milestone |
| --- | --- | --- |
| Weeks 5–6 | Fundraising strategy, round architecture, Target Investor Map, outreach build, pitch rehearsal (W5) | Strategy approved; outreach ready to launch |
| Weeks 7–9 | Outreach Wave 1, first meetings, feedback loop, materials iteration | Pipeline built; first investor meetings held |
| Weeks 10–12 | Outreach Wave 2, second meetings, partner meetings, early diligence | Qualified investors in active diligence |
| Weeks 13–14 | Diligence management, investor Q&A, syndicate construction | Diligence substantially complete |
| Weeks 15–16 | Term sheet, negotiation, legal coordination, signing and funding | Round closed |

Conditions attached to this timeline

The dates above are targets, not guarantees, and they assume:

The Client Input Pack is delivered within five business days of signature.

Founders attend all five workshops, with no more than one rescheduling per workshop.

Information requests are answered within five business days.

Deliverable review and approval is returned within three business days.

Introduced investors are responded to within three business days.

Where Btakka does not meet these conditions, the timeline extends day-for-day (Clause 7.2). Fundraising timelines additionally depend on market conditions and investor behaviour, neither of which is within the Consultant's control.

10. Fees

Fixed fee — EGP 150,000

| Milestone | Trigger | Amount | Cumulative |
| --- | --- | --- | --- |
| M1 — Deposit | On signature of this Agreement | EGP 30,000 | EGP 30,000 |
| M2 — Readiness complete | On sign-off of the Phase 1 data room readiness review | EGP 30,000 | EGP 60,000 |
| M3 — Closing | On First Close — first investment funds received in cleared funds | EGP 90,000 | EGP 150,000 |

M3 is payable whether the closing investor was introduced by the Consultant or sourced by Btakka. The work that makes a round closeable — the model, the valuation, the data room, the deck and the process — is delivered regardless of whose contact ultimately signs.

Success fee — 10%

10% of the aggregate Investment Amount funded by Consultant-Introduced Investors. No Success Fee is payable on tickets from investors Btakka sourced independently and who were never on the Target Investor Map or in an outreach wave.

Worked example:

| Total round closed | EGP 10,000,000 |
| --- | --- |
| — funded by Consultant-Introduced Investors | EGP 6,000,000 |
| — funded by Client-sourced investors | EGP 4,000,000 |
| Success Fee (10% × EGP 6,000,000) | EGP 600,000 |
| Fixed fee | EGP 150,000 |
| Total Consultant compensation | EGP 750,000 |

The Success Fee is payable per tranche, on amounts actually received in cleared funds. Attribution is governed by the Investor Log at Schedule E, which is maintained live and visible to Btakka throughout — there is no retrospective argument about who brought whom.

Total engagement value

EGP 150,000 fixed + 10% of Consultant-introduced tickets.

Full payment mechanics, taxes, expenses and treatment of non-cash consideration are at Clause 6 and Schedule D.

11. Assumptions and Exclusions

Assumptions

Btakka is a validly registered entity in the Arab Republic of Egypt with authority to raise investment.

The founding team is aligned on raising, on round size and on dilution tolerance.

Historic financial records exist in a reconstructable form, even if informal.

The founders are available for the workshop programme and for investor meetings.

Information provided to the Consultant is accurate, complete and not misleading.

Btakka has, or will appoint, Egyptian legal counsel for transaction documents.

Not included in this engagement

The following are outside scope. Any of them can be added by written variation.

| Excluded | Note |
| --- | --- |
| Legal drafting of transaction documents | Requires licensed Egyptian counsel; the Consultant reviews commercially and coordinates |
| Statutory audit or accounting bookkeeping | Requires a licensed auditor; the Consultant can refer |
| Tax and corporate structuring advice | Requires a licensed tax advisor |
| Company registration, licensing or regulatory filings | Client responsibility |
| Product development, design or engineering | Client responsibility |
| Brand identity creation | Btakka's existing brand guidelines are applied, not created |
| Paid data subscriptions, data room software, travel | Pre-approved pass-through cost (Clause 6.7) |
| Series A or any subsequent round | A new engagement |
| Debt arrangement, grant writing or soft-funding applications | Can be added by variation |
| Any guarantee that the round will be funded | See Clause 12 |

12. Why This Engagement

The work is done before the meeting, not during it. Most pre-seed companies start assembling a data room after an investor asks for one. By then the momentum is gone. This engagement front-loads the entire evidence package into four weeks so that outreach begins from a position of complete readiness.

The numbers are built to be attacked. Fifty-plus models built and reviewed means the model Btakka receives has already been stress-tested against the specific objections pre-seed investors raise in this market.

The founders keep the capability. The workshop structure exists so that Btakka's team can defend every assumption after the engagement ends — in this round and in the next one.

The incentives are aligned. EGP 90,000 of the fixed fee and the entire Success Fee sit behind a close. The Consultant is paid properly when Btakka is funded.

The process is transparent. Weekly pipeline reporting and a live Investor Log mean Btakka always knows exactly where the round stands.

PART II — CONSULTING AGREEMENT

Investment Readiness and Investment Round Management Services Agreement

This Agreement is made on [ ___ / ___ / 2026 ] (the "Effective Date")

BETWEEN:

(1) ABDELRHMAN SOLIMAN, an independent investment advisor and consultant, of Cairo, Arab Republic of Egypt, National ID / Tax Registration No. [ ], of [ address ] (the "Consultant"); and

(2) [ INSERT FULL REGISTERED LEGAL NAME ], trading as Btakka, a company registered in the Arab Republic of Egypt under Commercial Register No. [ ], Tax Card No. [ ], with its registered office at [ address ], represented by [ name ], [ title ] (the "Client").

The Consultant and the Client are each a "Party" and together the "Parties".

WHEREAS:

(A) The Client operates the mobile applications Btakka Business and Btakka Finishing & Decor and intends to raise a pre-seed investment round.

(B) The Consultant provides investment readiness, financial modelling, valuation, data room preparation and fundraising process management services.

(C) The Client wishes to engage the Consultant, and the Consultant agrees to be engaged, on the terms set out below.

NOW IT IS AGREED:

1. Definitions and Interpretation

1.1 In this Agreement:

| Term | Meaning |
| --- | --- |
| Agreement | This agreement, including Part I (Proposal) and Part III (Schedules) |
| Business Day | Any day other than Friday, Saturday or a public holiday in the Arab Republic of Egypt |
| Client Input Pack | The seven items listed at Part I §8 and Schedule C |
| Confidential Information | As defined at Clause 10.1 |
| Deliverables | The items listed at Part I §7 and Schedule A |
| Engagement Standard | The Client response obligations at Clause 5.3 |
| Final Close | The date the Round is declared closed by the Client or the target Round size is fully subscribed and funded, whichever is earlier |
| First Close | The date on which the first Investment Amount is received in cleared funds into the Client's bank account |
| Fixed Fee | EGP 150,000, payable per Clause 6.1 |
| Introduced Investor | An Investor falling within Clause 5.1 |
| Investment Amount | The aggregate consideration received by the Client in cleared funds in respect of a Ticket, comprising equity subscription proceeds, and proceeds under convertible or quasi-equity instruments including SAFEs and convertible notes at their face or principal amount. It excludes bank debt, commercial lending, government or institutional grants and non-dilutive soft funding, unless the Parties agree otherwise in writing |
| Investor | Any angel, syndicate, venture capital fund, family office, corporate or strategic investor, accelerator, investment vehicle or other provider of capital |
| Investor Log | The register maintained under Clause 5.2 in the form at Schedule E |
| Phase 1 | The Investment Readiness services at Part I §5 |
| Phase 2 | The Investment Round Management services at Part I §5 |
| Round | The pre-seed investment round contemplated by this Agreement |
| Services | Phase 1 and Phase 2 collectively |
| Success Fee | The fee payable under Clause 6.2 |
| Tail Period | Twelve (12) months from expiry or termination of this Agreement |
| Target Investor Map | The tiered investor target list delivered under Phase 2 Stage 1 |
| Ticket | An individual investment made into the Client as part of or in connection with the Round |

1.2 Headings are for convenience only. The singular includes the plural. "Including" means "including without limitation". References to a Clause or Schedule are to a clause or schedule of this Agreement.

1.3 In the event of conflict, the order of precedence is: Part II (this Agreement), then Part III (Schedules), then Part I (Proposal).

2. Appointment and Term

2.1 Appointment. The Client appoints the Consultant to provide the Services, and the Consultant accepts the appointment, on the terms of this Agreement.

2.2 Term. This Agreement commences on the Effective Date and continues until the earlier of (a) Final Close of the Round, (b) four (4) months from the Phase 1 Start Date as extended under Clause 7.2, or (c) termination under Clause 8. The Parties may extend by written agreement.

2.3 Phase 1 Start Date. Phase 1 commences on the later of (a) the Effective Date, (b) receipt of the M1 deposit under Clause 6.1, and (c) the date the Client Input Pack is received in full.

2.4 Non-exclusivity of the Consultant. The Consultant may provide services to other clients, including other companies, provided the Consultant does not act for a direct competitor of the Client in the same fundraising round without the Client's prior written consent.

2.5 Exclusivity of the Client. During Phase 2, the Client shall not appoint another advisor, agent, broker or intermediary to perform substantially the same Phase 2 fundraising process management services in respect of the Round, without the Consultant's prior written consent. This does not restrict the Client's own direct fundraising activity, which is expressly permitted and encouraged.

3. Services

3.1 Scope. The Consultant shall provide the Services described at Part I §5, deliver the Deliverables listed at Part I §7 and Schedule A, and conduct the workshop programme at Part I §6 and Schedule B.

3.2 Standard of performance. The Consultant shall perform the Services with reasonable skill, care and diligence, in accordance with the standards of a competent professional investment advisor, and in the Client's best interests.

3.3 Method and personnel. The Consultant shall determine the manner and method of performing the Services, and may engage subcontractors or specialist support at the Consultant's own cost, remaining fully responsible for their work and bound by Clause 10.

3.4 Phase 1 completion. Phase 1 is complete on the earlier of (a) the Client's written sign-off of the diligence readiness review, or (b) five (5) Business Days after the Consultant submits the readiness review, where the Client has not raised specific written objections within that period.

3.5 Revisions. Each Deliverable includes two (2) rounds of revision at no additional cost, where requested within ten (10) Business Days of delivery. Further revisions, or revisions arising from a material change in the Client's business, strategy or data after a Deliverable has been approved, are chargeable at EGP [ ___ ] per hour or by written variation.

3.6 Variation. Any change to scope, Deliverables, timeline or fees must be agreed in writing and signed by both Parties.

4. Client Obligations

4.1 Client Input Pack. The Client shall deliver the Client Input Pack in full within five (5) Business Days of the Effective Date.

4.2 Information. The Client shall provide all information, documents, data and access reasonably required by the Consultant, within five (5) Business Days of each request, and shall ensure that all information provided is accurate, complete, current and not misleading.

4.3 Workshops. The Client shall ensure that the required attendees listed at Schedule B attend each workshop. A workshop may be rescheduled once by either Party on not less than twenty-four (24) hours' notice. A second or subsequent rescheduling by the Client, or non-attendance without notice, is chargeable at fifty percent (50%) of the allocated session value and extends the timeline under Clause 7.2.

4.4 Approvals. The Client shall review and either approve or comment on each Deliverable within three (3) Business Days of delivery. A Deliverable not responded to within five (5) Business Days is deemed approved.

4.5 Point of contact. The Client shall nominate one individual, empowered to make decisions and give approvals binding on the Client, as the single point of contact for the engagement. Nominated: [ name ], [ title ], [ email ], [ mobile ].

4.6 Accuracy and disclosure. The Client is solely responsible for the accuracy and completeness of all information it supplies, and for all statements made to Investors. The Client shall disclose to the Consultant any fact, dispute, liability, contingent liability, regulatory matter or circumstance that a reasonable Investor would consider material.

4.7 Third-party advisors. The Client shall appoint and pay for its own legal, audit and tax advisors as required, and shall procure their timely cooperation.

4.8 Cooperation in good faith. The Client shall not take any step, or omit to take any step, that frustrates the performance of the Services or the progress of the Round.

5. Investor Introductions, Client Engagement and Attribution

This Clause is the commercial core of Phase 2. It defines who counts as an investor the Consultant brought, what the Client must do when one appears, and what happens if the Client does not.

5.1 Introduced Investor. An Investor is an "Introduced Investor" if the Consultant was the effective cause of the Client's contact with that Investor, including where the Consultant:

(a) made or arranged an introduction, referral or first contact, directly or through a third party;

(b) included the Investor on the Target Investor Map;

(c) included the Investor in an outreach wave, communication or campaign conducted under Phase 2;

(d) provided the Client with the Investor's identity or contact details in circumstances where the Client was not already in active discussion with that Investor; or

(e) materially facilitated, brokered or re-activated the relationship where contact had previously lapsed,

in each case where the relevant event is recorded in the Investor Log in accordance with Clause 5.2.

5.2 Investor Log. The Consultant shall maintain the Investor Log in the form at Schedule E, recording for each Investor the name, source, date of first contact and attribution. The Investor Log shall be shared with the Client weekly with the pipeline report. The Client may dispute any attribution entry by written notice within seven (7) Business Days of receipt of the report in which it first appears; absent such notice, the entry is final and binding. This mechanism exists so that attribution is settled contemporaneously and never retrospectively.

5.3 Engagement Standard. In respect of every Introduced Investor, the Client shall:

(a) respond substantively to any communication within three (3) Business Days;

(b) attend scheduled meetings, subject to no more than one (1) rescheduling per Investor;

(c) provide requested diligence materials within five (5) Business Days;

(d) notify the Consultant within two (2) Business Days of any direct contact with an Introduced Investor, and copy or brief the Consultant on material correspondence; and

(e) deal with each Introduced Investor professionally and in good faith.

5.4 Non-Engagement. Two (2) or more failures to meet the Engagement Standard, or any single failure continuing for more than ten (10) Business Days, constitutes "Non-Engagement". Non-Engagement is treated by the Parties as evidence that the Client is not seriously pursuing the Round. On Non-Engagement, the Consultant may, by written notice:

(a) suspend outreach and all Phase 2 activity, so as not to expose the Consultant's investor relationships to an unresponsive counterparty;

(b) stop the timeline clock under Clause 7.2, with all affected dates extending day-for-day;

(c) require the Client to cure within ten (10) Business Days; and

(d) if the Client does not cure, terminate under Clause 8.3, in which case all Fees accrued to the date of termination fall due immediately, and Clauses 6.2 and 9 continue to apply throughout the Tail Period.

5.5 Non-circumvention. The Client shall not, and shall procure that its founders, shareholders, officers, employees, affiliates and any entity under common control shall not, directly or indirectly, negotiate with, transact with, or accept investment from an Introduced Investor otherwise than under this Agreement, or in any manner structured to avoid or reduce the Success Fee. Any investment received in breach of this Clause is deemed to attract the Success Fee in full.

5.6 Attribution survives. The Success Fee is payable on any Ticket funded by an Introduced Investor whether the Ticket is funded during the Term or at any time within the Tail Period, and whether the final negotiation was conducted by the Consultant or by the Client.

5.7 No warranty as to Investors. The Consultant makes no representation or warranty as to the financial standing, willingness, capacity or conduct of any Investor. An introduction is not a recommendation to accept investment, and the Client is responsible for conducting its own diligence on any Investor before accepting funds.

5.8 Client-sourced investors. For the avoidance of doubt, an Investor sourced independently by the Client, not appearing on the Target Investor Map, not included in any outreach wave and not otherwise falling within Clause 5.1, is a "Client-Sourced Investor". No Success Fee is payable on a Client-Sourced Investor's Ticket. The M3 Closing Milestone under Clause 6.1 remains payable regardless of whether the First Close arises from an Introduced Investor or a Client-Sourced Investor.

6. Fees and Payment

6.1 Fixed Fee. The Client shall pay the Consultant a Fixed Fee of EGP 150,000 (One Hundred and Fifty Thousand Egyptian Pounds), as follows:

| Milestone | Trigger | Amount |
| --- | --- | --- |
| M1 — Deposit | On signature of this Agreement | EGP 30,000 |
| M2 — Readiness | On completion of Phase 1 under Clause 3.4 | EGP 30,000 |
| M3 — Closing | On First Close | EGP 90,000 |

(a) The M1 deposit is a non-refundable mobilisation fee and is payable before the Phase 1 Start Date.

(b) The M3 Closing Milestone Fee of EGP 90,000 shall become due upon First Close — being the date on which the first Investment Amount is received in cleared funds into the Client's bank account — irrespective of whether the Round remains open for subsequent tranches, and irrespective of whether the closing Investor was an Introduced Investor or a Client-Sourced Investor.

(c) If the Round has not reached First Close by the date this Agreement expires or is terminated other than under Clause 8.2, M3 remains payable on the first subsequent close occurring within the Tail Period.

6.2 Success Fee. In addition to the Fixed Fee, the Client shall pay the Consultant a Success Fee of ten percent (10%) of the aggregate Investment Amount funded by Introduced Investors.

(a) The Success Fee accrues per Ticket and is calculated on amounts actually received by the Client in cleared funds. Where a Ticket funds in tranches, the Success Fee is payable pro rata as each tranche is received.

(b) No Success Fee is payable in respect of a Client-Sourced Investor.

(c) Where consideration is received other than in cash, the Success Fee is calculated on the fair market value of that consideration as at the date of receipt, agreed between the Parties or, failing agreement within ten (10) Business Days, determined by an independent valuer jointly appointed and shared equally in cost.

(d) Where an Investment Amount is denominated in a currency other than Egyptian Pounds, it shall be converted at the Central Bank of Egypt mid-market rate on the date the funds are received in cleared funds.

(e) The Success Fee applies to Tickets funded during the Term and throughout the Tail Period, in accordance with Clauses 5.6 and 9.

6.3 Invoicing and payment. The Consultant shall issue an invoice on each Fee becoming due. Each invoice is payable within seven (7) Business Days of receipt, by bank transfer to the account nominated by the Consultant in writing. Payment obligations are not conditional on the Client's receipt of any third-party funds other than as expressly stated in the relevant trigger.

6.4 Late payment. Sums unpaid after the due date carry interest at one and a half percent (1.5%) per month on the outstanding balance, accruing daily from the due date until payment. Where any invoice remains unpaid for more than fifteen (15) Business Days, the Consultant may suspend the Services on written notice, without prejudice to any other right.

6.5 No set-off. All Fees are payable in full without set-off, counterclaim, deduction or withholding, save as required by law.

6.6 Taxes. All Fees are stated exclusive of Value Added Tax and any other applicable indirect tax, which the Client shall pay in addition where legally chargeable. Where the Client is required by Egyptian law to deduct withholding tax from a payment, it may do so, shall account for it to the Egyptian Tax Authority, and shall deliver to the Consultant the official withholding certificate within thirty (30) days of deduction. Each Party is responsible for its own income taxes.

6.7 Expenses. Fees exclude third-party costs — data room software subscriptions, paid market data, design licences, printing, and travel outside Greater Cairo. Such costs are chargeable at cost, and only where approved by the Client in writing in advance.

6.8 Currency. All Fees are payable in Egyptian Pounds unless otherwise agreed in writing.

7. Timeline and Delay

7.1 Target timeline. The Parties target four (4) weeks for Phase 1 from the Phase 1 Start Date, and three (3) months for Phase 2, as set out at Part I §9.

7.2 Client-caused delay. Where the Client fails to meet any obligation at Clause 4 or Clause 5.3, every affected date and the overall Term extends day-for-day by the period of delay, automatically and without the need for notice. The Consultant shall record delays in the weekly report.

7.3 Timeline is a target. The Client acknowledges that fundraising duration is materially affected by market conditions, investor availability and investor decision cycles, none of which are within the Consultant's control. The timelines in this Agreement are good-faith targets and are not conditions of the Agreement, warranties or guarantees, and failure to meet them does not of itself constitute a breach by the Consultant.

7.4 Extension. If the Round has not closed by the end of the Term, the Parties may extend Phase 2 by written agreement on terms to be agreed. Absent extension, Clauses 6.1(c), 6.2(e), 9 and 10 continue to apply.

8. Suspension and Termination

8.1 Termination for convenience. Either Party may terminate on thirty (30) days' written notice.

8.2 Termination by the Client for cause. The Client may terminate immediately on written notice if the Consultant commits a material breach that is not remedied within twenty (20) Business Days of written notice specifying the breach.

8.3 Termination by the Consultant for cause. The Consultant may terminate immediately on written notice if the Client:

(a) fails to pay any undisputed invoice within fifteen (15) Business Days of the due date;

(b) fails to cure Non-Engagement under Clause 5.4;

(c) breaches Clause 5.5 (non-circumvention);

(d) provides information the Consultant reasonably determines to be materially false or misleading; or

(e) requires the Consultant to act in a manner that is unlawful, or contrary to professional or ethical standards.

8.4 Insolvency. Either Party may terminate immediately if the other becomes insolvent, enters liquidation or bankruptcy, has a receiver appointed, or ceases to carry on business.

8.5 Consequences of termination. On termination:

(a) all Fees accrued or due to the date of termination become immediately payable, including any milestone already triggered;

(b) the M1 deposit is non-refundable in all circumstances;

(c) where termination occurs after Phase 1 is complete, M2 is payable in full;

(d) where the Client terminates under Clause 8.1, or the Consultant terminates under Clause 8.3, Clauses 5.5, 5.6, 6.1(c), 6.2 and 9 continue to apply for the Tail Period;

(e) where the Client terminates under Clause 8.2 for the Consultant's material breach, no further Fixed Fee milestone accrues after the date of termination, and the Success Fee remains payable only in respect of Tickets from Introduced Investors already recorded in the Investor Log at the date of termination;

(f) the Consultant shall deliver to the Client all completed Deliverables for which payment has been received, together with the data room and the Investor Log; and

(g) each Party shall return or destroy the other's Confidential Information on request, subject to Clause 10.5.

8.6 Suspension. The Consultant may suspend the Services under Clause 5.4(a) or Clause 6.4. Suspension does not relieve the Client of any accrued payment obligation, and the timeline extends by the period of suspension.

9. Tail Period

9.1 The Success Fee under Clause 6.2 and the Closing Milestone under Clause 6.1(c) remain payable in respect of any Ticket funded during the Tail Period of twelve (12) months following expiry or termination of this Agreement, where the Investor is an Introduced Investor recorded in the Investor Log at the date of expiry or termination.

9.2 The Client shall notify the Consultant in writing within ten (10) Business Days of any Ticket funded during the Tail Period, stating the Investor, the amount and the funding date.

9.3 The Consultant may, not more than twice during the Tail Period, request written confirmation from the Client of the status of the Round and of any Introduced Investor, and the Client shall respond within ten (10) Business Days.

10. Confidentiality

10.1 Definition. "Confidential Information" means all non-public information disclosed by one Party to the other in connection with this Agreement, including business plans, financial data and models, cap tables, customer and user data, product and technical information, investor identities and correspondence, valuations, and the terms of this Agreement.

10.2 Obligations. Each Party shall keep the other's Confidential Information confidential, use it only for the purposes of this Agreement, and not disclose it to any third party without prior written consent, save to professional advisors bound by equivalent obligations.

10.3 Disclosure to Investors. The Client authorises the Consultant to disclose Client Confidential Information to prospective Investors to the extent necessary to conduct the Round. The Consultant shall use reasonable endeavours to procure that data room access is granted under access control and, where the Client requires it, subject to a non-disclosure undertaking.

10.4 Exclusions. Confidential Information does not include information that is or becomes public other than through breach, was lawfully known before disclosure, is independently developed, or is required to be disclosed by law, court or regulator — in which case the disclosing Party shall, where lawful, give prior notice.

10.5 Duration and retention. This Clause survives for three (3) years after expiry or termination. The Consultant may retain one archival copy of engagement records for professional record-keeping and regulatory purposes, subject to continuing confidentiality.

10.6 Publicity. Neither Party shall make any public announcement regarding the Round without the other's prior written consent. The Client grants the Consultant the right to identify the Client by name and logo as a client, and to describe the engagement in general terms, in the Consultant's portfolio, website and marketing materials, after First Close — provided no confidential financial detail is disclosed. The Client may withdraw this permission by written notice.

11. Intellectual Property

11.1 Client materials. All intellectual property in materials supplied by the Client — including its brand, logos, product, screenshots, roadmap and business data — remains the Client's property. The Client grants the Consultant a non-exclusive licence to use those materials for the purposes of this Agreement.

11.2 Deliverables. On payment in full of the Fees due in respect of a Deliverable, all right, title and interest in that Deliverable transfers to the Client, and the Client may use, modify and distribute it without restriction.

11.3 Consultant know-how. The Consultant retains all rights in its pre-existing intellectual property, methodologies, model architectures, templates, frameworks and know-how, including as embodied in the Deliverables. Nothing in this Agreement transfers those rights. The Consultant grants the Client a perpetual, non-exclusive, royalty-free licence to use them to the extent embedded in a Deliverable, for the Client's own business purposes.

11.4 Retention of title pending payment. Until the Fees due in respect of a Deliverable are paid in full, the Consultant retains title in that Deliverable, and the Client shall not use it in any investor-facing communication.

12. No Guarantee of Funding; Nature of the Services

12.1 No guarantee. The Consultant does not guarantee, warrant or represent that the Round will be funded, that any Investor will invest, that any particular valuation will be achieved, or that any specific amount will be raised. Investment outcomes depend on market conditions, investor discretion and the Client's own performance and conduct.

12.2 Not regulated investment advice. The Services are commercial advisory, preparation and process-management services. Nothing provided under this Agreement constitutes investment advice, a recommendation to invest, a securities offering, an inducement, or a solicitation to any person to buy or sell securities.

12.3 Not a licensed intermediary. The Consultant is not a licensed securities broker, dealer, placement agent, or regulated financial intermediary, and does not hold itself out as such. The Fees payable under Clause 6, including the Success Fee, are consideration for the advisory, preparation, coordination and process-management Services described in this Agreement, and are not consideration for the offer, sale or placement of securities. Each Party has satisfied itself, and shall be responsible for satisfying itself, as to the treatment of this Agreement under applicable Egyptian financial services regulation, including the rules of the Financial Regulatory Authority, and each Party is advised to take its own independent legal advice on that question.

12.4 No legal, tax, audit or accounting advice. The Consultant does not provide legal, tax, audit, accounting or regulatory advice. The Client shall obtain such advice from appropriately licensed professionals. Any commercial commentary the Consultant provides on a term sheet or transaction document is commercial only and is not a substitute for legal advice.

12.5 Client decisions. All decisions as to whether to raise, from whom to raise, on what terms, and whether to accept any offer, rest exclusively with the Client.

13. Independent Contractor

13.1 The Consultant is an independent contractor. Nothing in this Agreement creates an employment relationship, partnership, joint venture, agency or fiduciary relationship between the Parties.

13.2 The Consultant is not authorised to enter into any contract, incur any liability, make any representation or accept any offer on the Client's behalf, unless expressly authorised in writing for a specific purpose.

13.3 The Consultant is responsible for the Consultant's own taxes, social insurance and statutory contributions.

14. Warranties and Limitation of Liability

14.1 Consultant warranty. The Consultant warrants that it has the right, capacity and skill to provide the Services, and will perform them in accordance with Clause 3.2.

14.2 Client warranties. The Client warrants that it is duly incorporated and validly existing; that it has full authority to enter into this Agreement and to raise the Round; that the person signing is duly authorised; and that all information it supplies is accurate, complete and not misleading.

14.3 Reliance. The Consultant relies on information supplied by the Client without independent verification. The Consultant is not liable for any loss arising from information that is inaccurate, incomplete, out of date or misleading, and the Client shall indemnify the Consultant against any third-party claim arising from such information, including any claim by an Investor.

14.4 Cap on liability. Subject to Clause 14.6, the Consultant's total aggregate liability arising out of or in connection with this Agreement, whether in contract, tort (including negligence), breach of statutory duty or otherwise, shall not exceed the total Fixed Fee actually paid by the Client to the Consultant under this Agreement.

14.5 Excluded loss. Neither Party is liable for loss of profit, loss of revenue, loss of anticipated savings, loss of business opportunity, loss of funding, dilution, or any indirect or consequential loss.

14.6 Unlimited liability. Nothing in this Agreement limits liability for fraud, fraudulent misrepresentation, wilful misconduct, or any liability that cannot lawfully be limited.

15. Force Majeure

15.1 Neither Party is liable for failure or delay in performance caused by an event beyond its reasonable control, including act of God, natural disaster, epidemic or pandemic, war, civil unrest, terrorism, governmental action, currency restriction, banking system failure, or prolonged failure of telecommunications or internet infrastructure.

15.2 The affected Party shall notify the other promptly. Performance is suspended for the duration of the event, and all timelines extend accordingly. If the event continues for more than sixty (60) consecutive days, either Party may terminate on written notice, and Clause 8.5 applies.

16. Notices

16.1 Notices under this Agreement shall be in writing and sent to the addresses below by email with confirmed delivery, by hand, or by registered post.

|  | Consultant | Client |
| --- | --- | --- |
| For the attention of | Abdelrhman Soliman | [ name ] |
| Email | abdelrhmansoliman96@gmail.com | [ email ] |
| Phone | +20 109 651 5287 | [ phone ] |
| Address | Cairo, Arab Republic of Egypt | [ address ] |

16.2 A notice is deemed received: if by email, on the next Business Day after sending, absent a delivery failure notification; if by hand, on delivery; if by registered post, five (5) Business Days after posting.

16.3 Routine operational communication, including weekly reports, the Investor Log and Deliverable delivery, may be conducted by email or the Parties' agreed project channel and does not require formal notice.

17. General

17.1 Entire agreement. This Agreement, comprising Parts I, II and III, constitutes the entire agreement between the Parties and supersedes all prior proposals, discussions, understandings and representations, whether written or oral.

17.2 Amendment. No amendment is effective unless in writing and signed by both Parties.

17.3 Waiver. No failure or delay in exercising a right constitutes a waiver of it. A waiver of one breach is not a waiver of any other.

17.4 Severability. If any provision is held invalid, illegal or unenforceable, it shall be modified to the minimum extent necessary to make it enforceable, or if that is not possible, severed. The remaining provisions continue in full force.

17.5 Assignment. Neither Party may assign or transfer this Agreement without the other's prior written consent, save that the Client may assign to a successor entity arising from a corporate reorganisation on written notice, provided all obligations under Clauses 5, 6 and 9 transfer with it.

17.6 Third-party rights. No person other than a Party has any right to enforce any term of this Agreement.

17.7 Survival. Clauses 5.5, 5.6, 6, 8.5, 9, 10, 11, 12, 14, 18 and this Clause 17 survive expiry or termination.

17.8 Counterparts and electronic signature. This Agreement may be executed in counterparts, each of which is an original and which together constitute one instrument. The Parties agree that signatures transmitted electronically, and electronic signatures made in accordance with Egyptian Law No. 15 of 2004 on E-Signature, are valid and binding.

17.9 Language. This Agreement is executed in English. If an Arabic translation is produced, the Parties shall specify in writing which version prevails; absent such specification, the English version prevails.

18. Governing Law and Dispute Resolution

18.1 Governing law. This Agreement and any dispute arising out of or in connection with it, including non-contractual disputes, are governed by the laws of the Arab Republic of Egypt.

18.2 Amicable settlement. The Parties shall first attempt in good faith to resolve any dispute by negotiation between senior representatives within thirty (30) days of written notice of the dispute.

18.3 Jurisdiction. If the dispute is not resolved under Clause 18.2, it shall be submitted to the exclusive jurisdiction of the competent Economic Courts of Cairo, Arab Republic of Egypt.

Alternative, to be selected before signature if preferred: the dispute shall be finally settled by arbitration under the Rules of the Cairo Regional Centre for International Commercial Arbitration (CRCICA), before a sole arbitrator, seated in Cairo, conducted in English, with the award final and binding.

19. Execution

IN WITNESS WHEREOF the Parties have executed this Agreement on the Effective Date first written above.

| THE CONSULTANT | THE CLIENT |
| --- | --- |
| ABDELRHMAN SOLIMAN | [ FULL REGISTERED LEGAL NAME ] trading as Btakka |
| Independent Investment Advisor & Consultant |  |
| Signature: ............................................. | Signature: ............................................. |
| Name: Abdelrhman Soliman | Name: ...................................................... |
| Title: Consultant | Title: ......................................................... |
| Date: ....................................................... | Date: ....................................................... |
|  | Company stamp: |

PART III — SCHEDULES

Schedule A — Data Room Scope and Responsibility Matrix

This Schedule maps every one of the 36 items in Btakka's Pre-Seed Round Data Room Checklist to an owner, so that there is no item without a name against it.

Owner key: C = Consultant prepares · B = Btakka provides · C+B = jointly produced, Btakka supplies the raw input and the Consultant produces the investor-facing version.

A.1 Company & Legal Documents

| # | Item | Priority | Owner | How it will be produced |
| --- | --- | --- | --- | --- |
| 1 | Certificate of Incorporation | High | B | Btakka supplies current certificate; Consultant indexes and checks currency |
| 2 | Cap Table (current) | High | C+B | Btakka supplies ownership data and any prior instruments; Consultant builds the modelled cap table with founder equity, existing investors and post-money dilution |
| 3 | Founder Agreements | High | B | Btakka supplies, including vesting schedules; Consultant reviews for investor-readiness gaps and flags issues to counsel |
| 4 | Previous Funding Documents | High | B | Btakka supplies all SAFEs, convertible notes, friends-and-family or pre-seed instruments; Consultant reflects them in the cap table and flags conversion mechanics |

A.2 Financial Documents

| # | Item | Priority | Owner | How it will be produced |
| --- | --- | --- | --- | --- |
| 5 | Financial Statements (last 6–12 months) | High | C+B | Btakka supplies records; Consultant structures management-prepared P&L and cash flow to investor format |
| 6 | Financial Projections | High | C | Driver-based model, 3–5 years, monthly for years 1–2, focused on near-term milestones |
| 7 | Use of Funds Statement | High | C | 12–18 month runway with milestone mapping against the raise |
| 8 | Current Cash Position | High | C+B | Btakka supplies bank balances; Consultant produces burn rate and runway analysis |
| 9 | Revenue Model Overview | High | C | Built from Btakka's business model across both product lines |
| 10 | Key Metrics Dashboard | Medium | C | Users, revenue, retention, engagement and unit economics, built from Btakka's data |

A.3 Product & Technology

| # | Item | Priority | Owner | How it will be produced |
| --- | --- | --- | --- | --- |
| 11 | Product Demo | High | C+B | Btakka supplies app screenshots and, if available, video; Consultant writes the demo script and walkthrough structure showing core functionality |
| 12 | Product Roadmap | High | C+B | Btakka supplies the roadmap; Consultant converts it to an investor-facing 6–12 month milestone view |
| 13 | User Feedback / Testimonials | High | B | Btakka supplies reviews, testimonials and early customer feedback; Consultant curates into a validation pack |
| 14 | Competitive Analysis | High | C | Competitor set, positioning map and differentiation thesis |
| 15 | Technical Overview | Medium | C+B | Btakka's technical lead briefs; Consultant writes the high-level stack and architecture summary |

A.4 Market & Traction

| # | Item | Priority | Owner | How it will be produced |
| --- | --- | --- | --- | --- |
| 16 | Market Size Analysis (TAM / SAM / SOM) | High | C | Sourced, defensible methodology focused on the addressable market |
| 17 | Early Traction Metrics | High | C+B | Btakka supplies raw data; Consultant builds the growth and momentum narrative |
| 18 | Customer Development | High | C+B | Btakka supplies interviews and validation evidence; Consultant structures the discovery evidence pack |
| 19 | Go-to-Market Strategy | High | C | Customer acquisition plan across both product lines |
| 20 | Early Customer List | Medium (optional) | B | Pilot customers or early adopters, if applicable |
| 21 | Partnership Opportunities | Low (optional) | B | Strategic partnerships, if relevant to the strategy |

A.5 Team & Founders

| # | Item | Priority | Owner | How it will be produced |
| --- | --- | --- | --- | --- |
| 22 | Founder Bios / Resumes | High | C+B | Btakka supplies CVs and photographs; Consultant writes investor-standard bios showing relevant experience |
| 23 | Key Hire Plan | High | C+B | Btakka supplies the HR plan; Consultant converts to a critical-roles hiring plan and costs it into the financial model |
| 24 | Organizational Chart | Medium | C+B | Current structure plus post-raise structure |
| 25 | Advisor List | Medium (optional) | B | Current advisors and backgrounds, if any |

A.6 Legal & Compliance

| # | Item | Priority | Owner | How it will be produced |
| --- | --- | --- | --- | --- |
| 26 | Legal Issues Disclosure | High | B | Full transparency required. Btakka discloses any legal matter, dispute or contingent liability; Consultant formats the disclosure |
| 27 | Business Registration | Medium | B | Business licence and registration documents |

A.7 Investor Materials

| # | Item | Priority | Owner | How it will be produced |
| --- | --- | --- | --- | --- |
| 28 | Pitch Deck | High | C | 10–15 slides: problem, solution, market, product, traction, business model, competition, team, financials, the ask. Designed to Btakka's brand guidelines |
| 29 | Business Plan (all parts) | High | C | Full narrative business plan carrying the investment thesis |
| 30 | Teaser | High | C | One-page designed summary for first-touch outreach |
| 31 | Term Sheet Template | High | C | Proposed terms reflecting Btakka's valuation expectations |
| 32 | Valuation | High | C | Pre-seed valuation with method, comparables and defensible range |
| 33 | References | Medium (optional) | B | Customer and advisor references for third-party validation |

A.8 Operations

| # | Item | Priority | Owner | How it will be produced |
| --- | --- | --- | --- | --- |
| 34 | Operational Metrics | Medium | C+B | Daily and weekly KPIs Btakka tracks; Consultant builds the reporting view |
| 35 | Key Vendor Agreements | Low (optional) | B | Critical service providers, where dependencies are significant |
| 36 | Insurance Coverage | Low (optional) | B | Basic business insurance, if held |

A.9 Summary

| Ownership | Items | Count |
| --- | --- | --- |
| Consultant prepares (C) | 6, 7, 9, 10, 14, 16, 19, 28, 29, 30, 31, 32 | 12 |
| Jointly produced (C+B) | 2, 5, 8, 11, 12, 15, 17, 18, 22, 23, 24, 34 | 12 |
| Btakka provides (B) | 1, 3, 4, 13, 20, 21, 25, 26, 27, 33, 35, 36 | 12 |
|  |  | 36 |

Of the 12 items Btakka provides outright, 7 are optional or conditional (20, 21, 25, 33, 35, 36 and, where none exist, 4). The mandatory Btakka-only burden is therefore limited to corporate documents, the legal disclosure and customer feedback.

Schedule B — Workshop Programme

B.1 Schedule

| # | Workshop | Week | Duration | Required attendees | Agenda | Output |
| --- | --- | --- | --- | --- | --- | --- |
| W1 | Discovery & Story Session | 1 | 3 hrs | All founders | Company history and origin; the problem and why now; product walkthrough of both apps; current traction and revenue; team; the raise and what it must achieve | Confirmed business understanding; investment thesis draft; consolidated information request list |
| W2 | Financial Modelling — Session 1 | 2 | 3 hrs | Founders + finance lead | Revenue engine and pricing; unit economics — CAC, payback, contribution margin, LTV; cost structure; headcount from the HR plan; the driver tree | Driver tree agreed; assumption book v1 signed off |
| W3 | Financial Modelling — Session 2 | 3 | 3 hrs | Founders + finance lead | Model walkthrough and challenge; base / conservative / upside scenarios; sensitivity testing; use of funds and milestone mapping; valuation method and range; cap table and dilution | Model approved; use of funds agreed; valuation range agreed |
| W4 | Full Data Room Workshop | 4 | 4 hrs | Full leadership team | Data room structure and index walkthrough; every item reviewed; diligence Q&A drill against the investor question bank; gap closure; access control and version discipline | Data room walkthrough complete; readiness sign-off; Phase 1 milestone M2 triggered |
| W5 | Investor Pitch Rehearsal | 5 | 2 hrs | Pitching founders | Live pitch delivery; timing and structure; objection handling drill; the hard questions; follow-up discipline | Pitch calibrated; founders cleared to go live |

B.2 Workshop conduct

Format. In person in Greater Cairo, or remotely by video, at Btakka's preference.

Recording. Sessions are recorded for Btakka's internal use, with consent recorded at the start of each session.

Follow-up. A written summary with decisions, assumptions agreed and action items is issued within two (2) Business Days.

Preparation. A pre-read and preparation list is issued at least two (2) Business Days before each session. Attendees are expected to have reviewed it.

Rescheduling. One reschedule per workshop is permitted on 24 hours' notice. Subsequent reschedules are chargeable under Clause 4.3.

Additional sessions. Beyond the five listed, additional workshops may be added by written variation.

Schedule C — Client Input Pack

Due: within five (5) Business Days of the Effective Date. The Phase 1 clock starts when the last item is received.

| # | Item | Specification | Received |
| --- | --- | --- | --- |
| 1 | Company profile | Overview, history, key milestones to date, legal structure, ownership, and a plain-language description of what Btakka does | ☐ |
| 2 | HR plan | Current headcount by role and function; current monthly salary cost per role; planned hires with role, seniority, start date and cost; any contractor or agency arrangements | ☐ |
| 3 | Roadmap | 6–12 month product development plan covering both applications, with milestones and target dates | ☐ |
| 4 | App screenshots | High-resolution screenshots of Btakka Business and Btakka Finishing & Decor, covering onboarding and the core user journeys, in PNG or JPG | ☐ |
| 5 | Founding team CVs and photos | Full CV for each founder and key team member; one professional photograph of each, minimum 1000px on the shortest side | ☐ |
| 6 | Brand guidelines | Brand book or style guide; vector logo files (AI, EPS or SVG); colour palette with hex values; typography and font files or names | ☐ |
| 7 | Business model | How Btakka earns revenue today and intends to, across both product lines, including pricing, commission or subscription structure, and any revenue actually collected to date | ☐ |

C.1 Supporting items required from Btakka

Requested formally at Workshop W1 as a single consolidated list, and required within five (5) Business Days of that request:

| Category | Items |
| --- | --- |
| Corporate | Certificate of Incorporation; business registration and licences; founder agreements including vesting; any prior funding instruments (SAFEs, convertible notes, friends-and-family) |
| Financial | Management accounts or financial records for the last 6–12 months; current bank balances; monthly burn; any outstanding liabilities or obligations |
| Traction | App analytics — downloads, installs, activations, active users, retention; transaction or order volume; revenue collected; any cohort data available |
| Customer | Customer or user interviews; reviews and testimonials; pilot or early customer list; any letters of intent |
| Legal | Disclosure of any dispute, claim, regulatory matter, IP issue or contingent liability |
| Optional | Advisor list; key vendor agreements; insurance policies; partnership discussions; customer and advisor references |

Schedule D — Fee Schedule and Payment Milestones

D.1 Fixed Fee — EGP 150,000

| Milestone | Trigger event | Evidence of trigger | Amount (EGP) | Invoice issued | Payment due |
| --- | --- | --- | --- | --- | --- |
| M1 — Deposit | Signature of this Agreement | Executed Agreement | 30,000 | On signature | Within 7 Business Days, and before the Phase 1 Start Date |
| M2 — Readiness | Completion of Phase 1 under Clause 3.4 | Client sign-off of the diligence readiness review, or deemed sign-off after 5 Business Days | 30,000 | On completion | Within 7 Business Days |
| M3 — Closing | First Close | Confirmation of funds received in cleared funds, from any Investor, Introduced or Client-Sourced | 90,000 | On First Close | Within 7 Business Days |
|  |  | Total Fixed Fee | 150,000 |  |  |

D.2 Success Fee — 10%

| Element | Term |
| --- | --- |
| Rate | 10% of the Investment Amount |
| Base | Aggregate Investment Amount funded by Introduced Investors only |
| Excluded | Tickets from Client-Sourced Investors (Clause 5.8) |
| Included instruments | Equity subscriptions; SAFEs and convertible notes at face or principal amount; quasi-equity |
| Excluded instruments | Bank debt, commercial lending, government or institutional grants, non-dilutive soft funding — unless agreed in writing |
| Trigger | Receipt of funds in cleared funds; payable pro rata per tranche |
| Invoice | Within 5 Business Days of each tranche being received |
| Payment due | Within 7 Business Days of invoice |
| Non-cash consideration | Valued at fair market value on receipt (Clause 6.2(c)) |
| Foreign currency | Converted at the CBE mid-market rate on the date of receipt (Clause 6.2(d)) |
| Tail | Payable on Introduced Investor Tickets funded within 12 months of expiry or termination (Clause 9) |

D.3 Worked scenarios

| Scenario | Round closed | Introduced by Consultant | Client-sourced | Fixed Fee | Success Fee | Total |
| --- | --- | --- | --- | --- | --- | --- |
| 1 — Consultant closes the full round | EGP 10,000,000 | EGP 10,000,000 | — | 150,000 | 1,000,000 | EGP 1,150,000 |
| 2 — Mixed round | EGP 10,000,000 | EGP 6,000,000 | EGP 4,000,000 | 150,000 | 600,000 | EGP 750,000 |
| 3 — Client closes the full round themselves | EGP 10,000,000 | — | EGP 10,000,000 | 150,000 | — | EGP 150,000 |
| 4 — Smaller round, all introduced | EGP 4,000,000 | EGP 4,000,000 | — | 150,000 | 400,000 | EGP 550,000 |
| 5 — Readiness completed, no close within Term or Tail | — | — | — | 60,000 | — | EGP 60,000 |

Scenarios are illustrative only and do not constitute a projection or expectation of round size.

D.4 Payment details

| Field | Detail |
| --- | --- |
| Payee | Abdelrhman Soliman |
| Bank | [ ] |
| Account number / IBAN | [ ] |
| SWIFT | [ ] |
| Currency | EGP |
| Payment method | Bank transfer |
| Payment terms | 7 Business Days from invoice |
| Late payment interest | 1.5% per month (Clause 6.4) |

Schedule E — Investor Log

Maintained by the Consultant, issued to Btakka weekly with the pipeline report. Attribution entries not disputed within seven (7) Business Days of first appearing are final (Clause 5.2).

E.1 Log format

| # | Investor name | Type | Attribution | First contact date | Source / warm path | Status | Ticket (EGP) | Funded date | Success Fee due |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 |  | Angel / Syndicate / VC / Family office / Corporate / Accelerator | Introduced / Client-Sourced |  |  | Contacted / Engaged / Meeting held / Diligence / Term sheet / Committed / Funded / Passed |  |  | Yes / No |
| 2 |  |  |  |  |  |  |  |  |  |
| 3 |  |  |  |  |  |  |  |  |  |

E.2 Status definitions

| Status | Meaning |
| --- | --- |
| Contacted | Outreach sent, no reply yet |
| Engaged | Investor has responded and is in dialogue |
| Meeting held | First meeting completed |
| Diligence | Investor has requested data room access or diligence materials |
| Term sheet | Investor has issued or indicated terms |
| Committed | Investor has signed and committed capital |
| Funded | Funds received in cleared funds — Success Fee trigger |
| Passed | Investor has declined; reason recorded |

E.3 Weekly pipeline report

Issued every week during Phase 2, covering: new investors contacted; responses received; meetings held and outcomes; investors in diligence; term sheets received; capital committed and funded to date against target; investor objections and how the materials were updated in response; Client actions outstanding; and any delay recorded under Clause 7.2.

Schedule F — Points to Confirm Before Signature

The following fields must be completed, and the following commercial points confirmed, before this Agreement is executed.

F.1 Fields to complete

| Ref | Field |
| --- | --- |
| Cover, Clause preamble | Client's full registered legal name, Commercial Register number, Tax Card number, registered address |
| Preamble | Consultant's National ID / Tax Registration number and address |
| Clause 4.5 | Client's nominated point of contact — name, title, email, mobile |
| Clause 3.5 | Hourly rate for out-of-scope revisions |
| Schedule D.4 | Consultant's bank account details |
| Clause 19 | Signature date, signatory names and titles |

F.2 Commercial points to confirm

| # | Point | Position drafted | To confirm |
| --- | --- | --- | --- |
| 1 | Target round size and instrument | Not yet fixed — to be set in W1 and the Phase 2 strategy | Btakka's target raise and preferred instrument |
| 2 | Grants, soft funding and debt | Excluded from the Success Fee base (Clause 1.1, Schedule D.2) | Whether Btakka intends to pursue grants or non-dilutive funding, and whether these should be brought into scope at a separate rate |
| 3 | Dispute resolution forum | Cairo Economic Courts (Clause 18.3) | Whether the Parties prefer CRCICA arbitration instead |
| 4 | Arabic version | English governs (Clause 17.9) | Whether a bilingual execution copy is required, and which language prevails |
| 5 | Regulatory treatment | Clause 12.3 — advisory fee, not placement | Each Party to take independent Egyptian legal advice on the treatment of a success-based fee under Financial Regulatory Authority rules |
| 6 | Phase 2 exclusivity | Consultant has exclusivity on process management; Btakka's own direct fundraising is permitted (Clause 2.5) | Confirm this is acceptable to Btakka |
| 7 | Data room platform | Not specified | Which platform will be used, and who pays for it (Clause 6.7) |

End of document.

Investment Readiness & Investment Round Management — Proposal and Consulting Agreement

Abdelrhman Soliman · Cairo, Egypt · abdelrhmansoliman96@gmail.com · +20 109 651 5287

Version 1.0 — For Client Review · 13 September 2026