Investment Readiness & Investment Round Management

Proposal

| Prepared for | Btakka — [Insert Registered Legal Entity Name] |
| --- | --- |
| Prepared by | Abdelrhman Soliman — Business & Investment Consultant |
| Date | 13 September 2026 |
| Validity of this proposal | 30 days from the date above |

Document Control

| Field | Detail |
| --- | --- |
| Document title | Investment Readiness & Investment Round Management — Proposal |
| Document 1 of 2 | This proposal describes the work. The accompanying Consulting Agreement sets the binding terms. |
| Version | 1.0 — For Client Review |
| Consultant | Abdelrhman Soliman, Business & Investment Consultant |
| Consultant contact | abdelrhmansoliman96@gmail.com · +20 109 651 5287 · Cairo, Egypt |
| Client (trade name) | Btakka |
| Client (legal entity) | [Insert full registered name] |
| Target round | Pre-Seed |
| Total engagement fee | EGP 150,000 plus a 10% Success Fee on Consultant-introduced tickets |
| Indicative duration | 4 months (1 month readiness + 3 months round management) |

How to read this document. Sections 1–13 set out the engagement: who is doing the work, what is delivered, by when, and for how much. Annexes A–C contain the detail — the full data room responsibility matrix, the workshop programme, and exactly what Btakka must provide. The binding terms are in the accompanying Consulting Agreement, referred to throughout as "the Consulting Agreement". Fields shown as [ ] are to be completed before signature.

THE ENGAGEMENT

1. Executive Summary

Btakka operates two published iOS products on the Egyptian App Store — Btakka Business (App Store) and Btakka Finishing & Decor (App Store). A live product in market is the hardest part of a pre-seed story, and Btakka already has it.

What most pre-seed companies in this position lack is not a product and not ambition — it is the evidence package. Investors do not fund a good idea described well. They fund a company that can answer every question in a diligence checklist within twenty-four hours, with numbers that reconcile, a story that holds under pressure, and a founder who has clearly done this work before the meeting rather than during it.

This engagement delivers exactly that, in two phases:

Phase 1 — Investment Readiness (1 month). Build the complete pre-seed data room against the 36-item checklist, the financial model and financial expectations, the valuation, the pitch deck, the teaser, the business plan and the full investor document set. Delivered through four structured workshops that transfer the reasoning to the founding team, not just the files.

Phase 2 — Investment Round Management (3 months). Convert readiness into capital: fundraising strategy, investor target map, structured outreach, meeting management, diligence coordination, term sheet negotiation and close.

Commercials. EGP 150,000 in fixed fees across four milestones (EGP 30,000 on signature, EGP 30,000 on completion of readiness, EGP 20,000 on launch of investor outreach, EGP 70,000 on first close), plus a 10% Success Fee on the value of investment tickets funded by investors the Consultant introduced.

The one thing that determines whether this works. Every deadline in this document is conditional on Btakka's engagement — documents delivered on time, workshops attended by decision-makers, and introduced investors answered within three business days. This is stated plainly in Clause 5 and Clause 7 of the accompanying Consulting Agreement because it is the single largest cause of failed rounds, and it is the one input the Consultant cannot supply.

2. About the Consultant

Abdelrhman Soliman is an independent investment advisor based in Cairo, working with founders, angels, VCs and family offices across MENA and global markets. Specialisations: investment evaluation, fundraising strategy, investor relations, financial modelling and portfolio development.

Track record

| Metric | Figure |
| --- | --- |
| Years in VC, PE and advisory | 7+ |
| Startups mentored | 100+ |
| Capital raised supported | USD 10M+ |
| Financial models built and reviewed | 50+ |

Recognition

Top 4% — VC Lab, Cohort 17. Among the top 4% of emerging fund managers globally; validated a USD 3M pre-seed SaaS fund thesis.

Winner — Fintech Saudi 2024 Content Challenge, for "Reimagining the Financial Services Value Chain".

Top 10 LinkedIn VC Creators, MENA, for thought leadership and founder education.

Credentials

CFA Level I (CFA Institute) · VC & Private Equity (Bocconi) · Advanced Valuation (Erasmus Rotterdam) · Investment Banking virtual experience (J.P. Morgan) · Alternative Investing (Apollo Academy).

Sectors covered

SaaS · Fintech · E-commerce · Real Estate · Ed-tech · Logistics · Climate Tech · Retail.

Speaking and media

Startupbootcamp · VC4A · Startup Without Borders · TINTS Business Lobby · Asharq News (Sharq Bounce) · Alhadath Alyoum TV (Financial Market) · Investment World LinkedIn newsletter · YouTube founder-education channel.

3. Understanding of Btakka

The Consultant's present understanding is based on the two publicly listed applications and the materials shared to date. It will be confirmed, corrected and completed in the Discovery & Story Workshop (W1), which is scheduled as the first substantive session of the engagement precisely so that no downstream deliverable is built on an assumption.

| What is established | What will be established in W1 |
| --- | --- |
| Two live iOS products published on the Egyptian App Store | Current traction: downloads, activations, active users, retention |
| A B2B/business-facing product (Btakka Business) | Revenue model in force today and monetisation actually collected |
| A vertical product for finishing and décor | Unit economics: CAC, payback, contribution margin, LTV |
| The company is at pre-seed stage and raising | Target round size, instrument, valuation expectation and use of funds |
| A founding team is in place | Cap table, prior funding, founder vesting, current runway and burn |
| A product roadmap exists | Competitive set, defensibility and the wedge into the market |

Why this matters. A pre-seed investor in Egypt is underwriting three things: that the market is large enough, that this team can execute, and that the money buys a specific, measurable step-change. The data room is the instrument that proves all three. Everything in Phase 1 is built to answer those three questions and nothing else.

4. Engagement Objective

To take Btakka from its current position to a funded pre-seed round, by:

Producing an investor-grade data room covering all 36 items of the Pre-Seed Round Data Room Checklist.

Producing a defensible financial model, financial expectations and valuation that withstand investor scrutiny.

Producing the complete investor document set — pitch deck, teaser, business plan, term sheet template and valuation.

Equipping the founding team, through workshops, to own and defend every number and every claim.

Running a structured, time-boxed fundraising process from strategy through outreach to signed close.

What "success" means in this document. Phase 1 succeeds when the data room passes a diligence readiness review and is signed off (Annex A). Phase 2 succeeds when investment funds are received in cleared funds in Btakka's account. The Consultant does not, and cannot, guarantee that a round will be funded — see Clause 12 of the Consulting Agreement.

5. Scope of Work

Phase 1 — Investment Readiness (Weeks 1–4)

Workstream A — Story, Positioning & Market

Investment thesis and narrative spine for Btakka

Problem/solution framing calibrated to pre-seed investor expectations

Market sizing: TAM, SAM and SOM with sourced, defensible methodology

Competitive analysis and differentiation map

Go-to-market strategy and customer acquisition plan

Customer development evidence pack and traction narrative

Workstream B — Financial Model, Expectations & Valuation

Full driver-based financial model, 3–5 year horizon, monthly for year 1–2

Revenue model across both product lines, built on real unit economics

Cost structure: COGS, operating expenses, and headcount costs derived from Btakka's HR plan

Cash flow, burn rate, runway and current cash position statement

Financial expectations pack — the forward projections investors will underwrite

Use of Funds statement covering a 12–18 month runway with milestone mapping

Pre-seed valuation with method, comparables and a defensible range

Current and post-money cap table, including dilution scenarios

Key metrics dashboard and operational KPI set

Workstream C — Data Room Construction

Full data room architecture, folder structure, naming convention and index

Preparation, drafting or investor-formatting of every Consultant-owned item in Annex A

Collection, review and quality control of every Client-provided item in Annex A

Gap analysis and a remediation list for anything missing, weak or inconsistent

Diligence Q&A bank — the questions investors will ask, with prepared answers

Access control, permissioning and version discipline

Final diligence readiness review and sign-off

Workstream D — Investor Document Set

Pitch deck — 10–15 slides: problem, solution, market, product, traction, business model, competition, team, financials, the ask

Teaser — one-page designed summary for first-touch outreach

Business plan — full narrative document, all parts

Term sheet template — proposed investment terms reflecting Btakka's valuation expectations

Valuation document — method, assumptions, comparables and conclusion

Founder bios written to investor standard, from the CVs provided

Product demo script and walkthrough structure built around the app screenshots provided

Phase 2 — Investment Round Management (Months 2–4)

Stage 1 — Fundraising Strategy (Weeks 5–6)

Round architecture: size, instrument (equity / SAFE / convertible note), valuation and terms

Investor segmentation: angels, syndicates, pre-seed funds, family offices, strategic and corporate investors, accelerators and relevant Egyptian and regional programmes

Target Investor Map with prioritised tiers, thesis fit and warm-path mapping

Outreach infrastructure: sequencing, messaging, channel plan and tracking

Pitch rehearsal and objection handling with the founding team

Round timeline with weekly milestones and a defined close target

Stage 2 — Outreach & Investor Engagement (Weeks 7–12)

Structured outreach waves against the Target Investor Map

Warm introductions through the Consultant's network where available

Teaser and deck distribution under version and access control

Meeting scheduling, preparation briefs and post-meeting debriefs

Investor feedback captured, analysed and fed back into the materials

Weekly pipeline reporting: contacted, engaged, in diligence, term sheet, closed

Iteration of deck, model and data room in response to real investor objections

Stage 3 — Diligence, Negotiation & Close (Weeks 13–16)

Diligence management: request coordination, response drafting, data room administration

Investor question handling and escalation

Term sheet review, commercial commentary and negotiation support

Valuation and dilution modelling across competing offers

Syndicate construction where multiple investors participate

Coordination with Btakka's legal counsel through to signing and funding

Post-close investor reporting structure and investor update template

6. Workshop Programme

Workshops are the mechanism by which the reasoning behind every deliverable is transferred to the founding team. A founder who cannot defend their own model in a meeting does not get funded, regardless of how good the model is.

| # | Workshop | Timing | Duration | Required attendees | Output |
| --- | --- | --- | --- | --- | --- |
| W1 | Discovery & Story Session — initial meeting to understand the story | Week 1 | 3 hours | All founders | Confirmed business understanding, investment thesis draft, full information request list |
| W2 | Financial Modelling Workshop — Session 1 | Week 2 | 3 hours | Founders + finance lead | Driver tree, unit economics, assumption book v1 |
| W3 | Financial Modelling Workshop — Session 2 | Week 3 | 3 hours | Founders + finance lead | Model review and challenge, use of funds, valuation range |
| W4 | Full Data Room Workshop | Week 4 | 4 hours | Full leadership team | Complete data room walkthrough, diligence Q&A drill, readiness sign-off |
| W5 | Investor Pitch Rehearsal | Week 5 | 2 hours | Pitching founders | Pitch calibration, objection handling, go-live sign-off |

All workshops may be held in person in Cairo or remotely by video, at Btakka's preference. Sessions are recorded and a written summary with action items is issued within two business days. Full detail is at Annex B.

7. Deliverables

Every deliverable below is produced by the Consultant and handed over in both editable source format and a final PDF, except where noted.

How delivery divides. The Consultant prepares the investment documents — the financial model, financial expectations, valuation, cap table, use of funds, market sizing, competitive analysis, go-to-market strategy, metrics dashboard, pitch deck, teaser, business plan and term sheet template. Btakka delivers the remaining documents together with the Consultant — the corporate, legal, financial-record, product, traction and customer materials. Annex A sets out which of the 36 data room items falls where, and Clause 3.7 of the Consulting Agreement makes the division binding.

Phase 1 deliverables

| # | Deliverable | Format | Due by |
| --- | --- | --- | --- |
| 1 | Data room architecture and index | Folder structure + index sheet | Week 1 |
| 2 | Information request list and gap analysis | Tracker | Week 1 |
| 3 | Investment thesis and narrative spine | Document | Week 2 |
| 4 | Market sizing — TAM / SAM / SOM | Document + model | Week 2 |
| 5 | Competitive analysis | Document | Week 2 |
| 6 | Financial model (driver-based, 3–5 years) | Excel | Week 3 |
| 7 | Financial expectations pack | Excel + document | Week 3 |
| 8 | Revenue model overview | Document | Week 3 |
| 9 | Use of Funds statement | Document | Week 3 |
| 10 | Cap table (current and post-money) | Excel | Week 3 |
| 11 | Valuation document | Document + model | Week 3 |
| 12 | Key metrics dashboard | Excel | Week 3 |
| 13 | Go-to-market strategy | Document | Week 3 |
| 14 | Pitch deck (10–15 slides) | Designed deck + source | Week 4 |
| 15 | Teaser (one page, designed) | Designed PDF + source | Week 4 |
| 16 | Business plan (all parts) | Document | Week 4 |
| 17 | Term sheet template | Document | Week 4 |
| 18 | Founder bios (investor standard) | Document | Week 4 |
| 19 | Product demo script and walkthrough | Document | Week 4 |
| 20 | Technical overview | Document | Week 4 |
| 21 | Organisational chart and key hire plan | Document | Week 4 |
| 22 | Diligence Q&A bank | Document | Week 4 |
| 23 | Complete, indexed, populated data room | Live data room | Week 4 |
| 24 | Diligence readiness review and sign-off | Report | Week 4 |

Phase 2 deliverables

| # | Deliverable | Format | Due by |
| --- | --- | --- | --- |
| 25 | Fundraising strategy document | Document | Week 6 |
| 26 | Round architecture and terms recommendation | Document | Week 6 |
| 27 | Target Investor Map (tiered, with warm paths) | Tracker | Week 6 |
| 28 | Outreach plan, sequences and messaging | Document | Week 6 |
| 29 | Investor Log (maintained live) | Tracker | Weekly from Week 7 |
| 30 | Weekly pipeline report | Report | Every week, Weeks 7–16 |
| 31 | Meeting preparation briefs and debriefs | Documents | Per meeting |
| 32 | Investor feedback analysis and materials iteration | Report + updated materials | Rolling |
| 33 | Diligence response coordination pack | Documents | As required |
| 34 | Term sheet review and negotiation commentary | Document | On receipt |
| 35 | Dilution and offer comparison model | Excel | On receipt |
| 36 | Investor update template and reporting structure | Template | At close |
| 37 | Engagement closing report and handover | Report | At close |

8. What Btakka Must Provide

The engagement cannot start without the Client Input Pack. These seven items are required within five business days of signature, and the Phase 1 clock starts on the date the last of them is received.

| # | Item | What is needed | Format |
| --- | --- | --- | --- |
| 1 | Company profile | Company overview, history, milestones, legal structure, what Btakka does in the founders' own words | Document |
| 2 | HR plan | Current headcount by role, current salary cost, planned hires with roles, timing and cost | Excel or document |
| 3 | Product roadmap | 6–12 month development plan with milestones for both applications | Document or board export |
| 4 | App screenshots | High-resolution screenshots of both applications covering the core user journeys | PNG or JPG, high resolution |
| 5 | Founding team CVs and photos | Full CV for each founder and key team member, plus a professional photograph of each | PDF + image files |
| 6 | Brand guidelines | Logo files, colour palette, typography, and any existing brand or design system | Brand book + vector logo files |
| 7 | Business model | How Btakka makes money today and intends to, across both product lines, with pricing | Document |

In addition, the items marked Client in Annex A are required — principally the legal and corporate documents, historic financial statements, bank balances, traction data and customer evidence. The Consultant will issue a single consolidated request list at Workshop W1 so that nothing is requested twice.

Btakka must also provide: a single named point of contact empowered to make decisions; founder availability for the five workshops; responses to information requests within five business days; and responses to introduced investors within three business days (Clause 5 of the Consulting Agreement).

9. Timeline

Phase 1 — Investment Readiness: 4 weeks

| Week | Focus | Workshop | Milestone |
| --- | --- | --- | --- |
| Week 0 | Signature, deposit, NDA, Client Input Pack request, data room provisioning | — | Engagement mobilised |
| Week 1 | Discovery, business deep dive, information collection, data room architecture | W1 | Information request issued; data room structure live |
| Week 2 | Market sizing, competitive analysis, thesis, model build begins | W2 | Assumption book agreed; market pack delivered |
| Week 3 | Model completion, use of funds, valuation, cap table | W3 | Financial model, expectations and valuation delivered |
| Week 4 | Investor document set, data room population, readiness review | W4 | Phase 1 complete — data room signed off |

Phase 2 — Investment Round Management: 3 months

| Period | Focus | Milestone |
| --- | --- | --- |
| Weeks 5–6 | Fundraising strategy, round architecture, Target Investor Map, outreach build, pitch rehearsal (W5) | Strategy approved; outreach ready to launch |
| Weeks 7–9 | Outreach Wave 1, first meetings, feedback loop, materials iteration | Pipeline built; first investor meetings held |
| Weeks 10–12 | Outreach Wave 2, second meetings, partner meetings, early diligence | Qualified investors in active diligence |
| Weeks 13–14 | Diligence management, investor Q&A, syndicate construction | Diligence substantially complete |
| Weeks 15–16 | Term sheet, negotiation, legal coordination, signing and funding | Round closed |

Conditions attached to this timeline

The dates above are targets, not guarantees, and they assume:

The Client Input Pack is delivered within five business days of signature.

Founders attend all five workshops, with no more than one rescheduling per workshop.

Information requests are answered within five business days.

Deliverable review and approval is returned within three business days.

Introduced investors are responded to within three business days.

Where Btakka does not meet these conditions, the timeline extends day-for-day (Clause 7.2 of the Consulting Agreement). Fundraising timelines additionally depend on market conditions and investor behaviour, neither of which is within the Consultant's control.

10. Fees

Fixed fee — EGP 150,000

| Milestone | Trigger | Amount | Cumulative |
| --- | --- | --- | --- |
| M1 — Down payment | On signature of this Agreement | EGP 30,000 | EGP 30,000 |
| M2 — Readiness complete | On sign-off of the Phase 1 data room readiness review | EGP 30,000 | EGP 60,000 |
| M3 — Round | On launch of the first investor outreach wave | EGP 20,000 | EGP 80,000 |
| M4 — Closing | On First Close — first investment ticket received in cleared funds | EGP 70,000 | EGP 150,000 |

M4 is payable whether the closing investor was introduced by the Consultant or sourced by Btakka. The work that makes a round closeable — the model, the valuation, the data room, the deck and the process — is delivered regardless of whose contact ultimately signs.

Success fee — 10%

10% of the aggregate Investment Amount funded by Consultant-Introduced Investors. No Success Fee is payable on tickets from investors Btakka sourced independently and who were never on the Target Investor Map or in an outreach wave.

Worked example:

| Total round closed | EGP 10,000,000 |
| --- | --- |
| — funded by Consultant-Introduced Investors | EGP 6,000,000 |
| — funded by Client-sourced investors | EGP 4,000,000 |
| Success Fee (10% × EGP 6,000,000) | EGP 600,000 |
| Fixed fee | EGP 150,000 |
| Total Consultant compensation | EGP 750,000 |

The Success Fee is payable per tranche, on amounts actually received in cleared funds. Attribution is governed by the Investor Log at Schedule 3 to the Consulting Agreement, which is maintained live and visible to Btakka throughout — there is no retrospective argument about who brought whom.

Total engagement value

EGP 150,000 fixed + 10% of Consultant-introduced tickets.

Full payment mechanics, taxes, expenses and treatment of non-cash consideration are at Clause 6 of, and Schedule 2 to, the accompanying Consulting Agreement.

11. Assumptions and Exclusions

Assumptions

Btakka is a validly registered entity in the Arab Republic of Egypt with authority to raise investment.

The founding team is aligned on raising, on round size and on dilution tolerance.

Historic financial records exist in a reconstructable form, even if informal.

The founders are available for the workshop programme and for investor meetings.

Information provided to the Consultant is accurate, complete and not misleading.

Btakka has, or will appoint, Egyptian legal counsel for transaction documents.

Not included in this engagement

The following are outside scope. Any of them can be added by written variation.

| Excluded | Note |
| --- | --- |
| Legal drafting of transaction documents | Requires licensed Egyptian counsel; the Consultant reviews commercially and coordinates |
| Statutory audit or accounting bookkeeping | Requires a licensed auditor; the Consultant can refer |
| Tax and corporate structuring advice | Requires a licensed tax advisor |
| Company registration, licensing or regulatory filings | Client responsibility |
| Product development, design or engineering | Client responsibility |
| Brand identity creation | Btakka's existing brand guidelines are applied, not created |
| Paid data subscriptions, data room software, travel | Pre-approved pass-through cost (Clause 6.7 of the Consulting Agreement) |
| Series A or any subsequent round | A new engagement |
| Debt arrangement, grant writing or soft-funding applications | Can be added by variation |
| Any guarantee that the round will be funded | See Clause 12 of the Consulting Agreement |

12. Why This Engagement

The work is done before the meeting, not during it. Most pre-seed companies start assembling a data room after an investor asks for one. By then the momentum is gone. This engagement front-loads the entire evidence package into four weeks so that outreach begins from a position of complete readiness.

The numbers are built to be attacked. Fifty-plus models built and reviewed means the model Btakka receives has already been stress-tested against the specific objections pre-seed investors raise in this market.

The founders keep the capability. The workshop structure exists so that Btakka's team can defend every assumption after the engagement ends — in this round and in the next one.

The incentives are aligned. EGP 70,000 of the fixed fee and the entire Success Fee sit behind a close. The Consultant is paid properly when Btakka is funded.

The process is transparent. Weekly pipeline reporting and a live Investor Log mean Btakka always knows exactly where the round stands.

13. How to Proceed

This proposal is accompanied by a Consulting Agreement — the binding contract that gives effect to everything described here. The proposal explains the work; the Agreement sets the terms.

| Step | Action | Who | When |
| --- | --- | --- | --- |
| 1 | Review this proposal and the accompanying Consulting Agreement | Btakka | — |
| 2 | Agree the open commercial points the Consultant raises — target round size and instrument, dispute forum, whether an Arabic execution copy is needed, and the data room platform | Both | Before signature |
| 3 | Complete the blank fields in the Agreement — legal entity name, Commercial Register and Tax Card numbers, registered address, nominated point of contact | Btakka | Before signature |
| 4 | Sign the Consulting Agreement | Both | Effective Date |
| 5 | Pay the M1 down payment of EGP 30,000 | Btakka | On signature |
| 6 | Deliver the Client Input Pack — the seven items at section 8 and Annex C | Btakka | Within 5 business days of signature |
| 7 | Discovery & Story Workshop (W1) | Both | Week 1 |

The Phase 1 clock starts on the date the last item of the Client Input Pack is received, not on the signature date. Delivering that pack quickly is the single fastest way to bring the close date forward.

This proposal is valid for 30 days from 13 September 2026.

Contact

| Abdelrhman Soliman | Business & Investment Consultant |
| --- | --- |
| Email | abdelrhmansoliman96@gmail.com |
| Phone | +20 109 651 5287 |
| Location | Cairo, Arab Republic of Egypt |

ANNEXES

Annex A — Data Room Scope and Responsibility Matrix

This Annex maps every one of the 36 items in Btakka's Pre-Seed Round Data Room Checklist to an owner, so that there is no item without a name against it.

Owner key: C = Consultant prepares · B = Btakka provides · C+B = jointly produced, Btakka supplies the raw input and the Consultant produces the investor-facing version.

A.1 Company & Legal Documents

| # | Item | Priority | Owner | How it will be produced |
| --- | --- | --- | --- | --- |
| 1 | Certificate of Incorporation | High | B | Btakka supplies current certificate; Consultant indexes and checks currency |
| 2 | Cap Table (current) | High | C+B | Btakka supplies ownership data and any prior instruments; Consultant builds the modelled cap table with founder equity, existing investors and post-money dilution |
| 3 | Founder Agreements | High | B | Btakka supplies, including vesting schedules; Consultant reviews for investor-readiness gaps and flags issues to counsel |
| 4 | Previous Funding Documents | High | B | Btakka supplies all SAFEs, convertible notes, friends-and-family or pre-seed instruments; Consultant reflects them in the cap table and flags conversion mechanics |

A.2 Financial Documents

| # | Item | Priority | Owner | How it will be produced |
| --- | --- | --- | --- | --- |
| 5 | Financial Statements (last 6–12 months) | High | C+B | Btakka supplies records; Consultant structures management-prepared P&L and cash flow to investor format |
| 6 | Financial Projections | High | C | Driver-based model, 3–5 years, monthly for years 1–2, focused on near-term milestones |
| 7 | Use of Funds Statement | High | C | 12–18 month runway with milestone mapping against the raise |
| 8 | Current Cash Position | High | C+B | Btakka supplies bank balances; Consultant produces burn rate and runway analysis |
| 9 | Revenue Model Overview | High | C | Built from Btakka's business model across both product lines |
| 10 | Key Metrics Dashboard | Medium | C | Users, revenue, retention, engagement and unit economics, built from Btakka's data |

A.3 Product & Technology

| # | Item | Priority | Owner | How it will be produced |
| --- | --- | --- | --- | --- |
| 11 | Product Demo | High | C+B | Btakka supplies app screenshots and, if available, video; Consultant writes the demo script and walkthrough structure showing core functionality |
| 12 | Product Roadmap | High | C+B | Btakka supplies the roadmap; Consultant converts it to an investor-facing 6–12 month milestone view |
| 13 | User Feedback / Testimonials | High | B | Btakka supplies reviews, testimonials and early customer feedback; Consultant curates into a validation pack |
| 14 | Competitive Analysis | High | C | Competitor set, positioning map and differentiation thesis |
| 15 | Technical Overview | Medium | C+B | Btakka's technical lead briefs; Consultant writes the high-level stack and architecture summary |

A.4 Market & Traction

| # | Item | Priority | Owner | How it will be produced |
| --- | --- | --- | --- | --- |
| 16 | Market Size Analysis (TAM / SAM / SOM) | High | C | Sourced, defensible methodology focused on the addressable market |
| 17 | Early Traction Metrics | High | C+B | Btakka supplies raw data; Consultant builds the growth and momentum narrative |
| 18 | Customer Development | High | C+B | Btakka supplies interviews and validation evidence; Consultant structures the discovery evidence pack |
| 19 | Go-to-Market Strategy | High | C | Customer acquisition plan across both product lines |
| 20 | Early Customer List | Medium (optional) | B | Pilot customers or early adopters, if applicable |
| 21 | Partnership Opportunities | Low (optional) | B | Strategic partnerships, if relevant to the strategy |

A.5 Team & Founders

| # | Item | Priority | Owner | How it will be produced |
| --- | --- | --- | --- | --- |
| 22 | Founder Bios / Resumes | High | C+B | Btakka supplies CVs and photographs; Consultant writes investor-standard bios showing relevant experience |
| 23 | Key Hire Plan | High | C+B | Btakka supplies the HR plan; Consultant converts to a critical-roles hiring plan and costs it into the financial model |
| 24 | Organizational Chart | Medium | C+B | Current structure plus post-raise structure |
| 25 | Advisor List | Medium (optional) | B | Current advisors and backgrounds, if any |

A.6 Legal & Compliance

| # | Item | Priority | Owner | How it will be produced |
| --- | --- | --- | --- | --- |
| 26 | Legal Issues Disclosure | High | B | Full transparency required. Btakka discloses any legal matter, dispute or contingent liability; Consultant formats the disclosure |
| 27 | Business Registration | Medium | B | Business licence and registration documents |

A.7 Investor Materials

| # | Item | Priority | Owner | How it will be produced |
| --- | --- | --- | --- | --- |
| 28 | Pitch Deck | High | C | 10–15 slides: problem, solution, market, product, traction, business model, competition, team, financials, the ask. Designed to Btakka's brand guidelines |
| 29 | Business Plan (all parts) | High | C | Full narrative business plan carrying the investment thesis |
| 30 | Teaser | High | C | One-page designed summary for first-touch outreach |
| 31 | Term Sheet Template | High | C | Proposed terms reflecting Btakka's valuation expectations |
| 32 | Valuation | High | C | Pre-seed valuation with method, comparables and defensible range |
| 33 | References | Medium (optional) | B | Customer and advisor references for third-party validation |

A.8 Operations

| # | Item | Priority | Owner | How it will be produced |
| --- | --- | --- | --- | --- |
| 34 | Operational Metrics | Medium | C+B | Daily and weekly KPIs Btakka tracks; Consultant builds the reporting view |
| 35 | Key Vendor Agreements | Low (optional) | B | Critical service providers, where dependencies are significant |
| 36 | Insurance Coverage | Low (optional) | B | Basic business insurance, if held |

A.9 Summary

| Ownership | Items | Count |
| --- | --- | --- |
| Consultant prepares (C) | 6, 7, 9, 10, 14, 16, 19, 28, 29, 30, 31, 32 | 12 |
| Jointly produced (C+B) | 2, 5, 8, 11, 12, 15, 17, 18, 22, 23, 24, 34 | 12 |
| Btakka provides (B) | 1, 3, 4, 13, 20, 21, 25, 26, 27, 33, 35, 36 | 12 |
|  |  | 36 |

Of the 12 items Btakka provides outright, 7 are optional or conditional (20, 21, 25, 33, 35, 36 and, where none exist, 4). The mandatory Btakka-only burden is therefore limited to corporate documents, the legal disclosure and customer feedback.

Annex B — Workshop Programme

B.1 Schedule

| # | Workshop | Week | Duration | Required attendees | Agenda | Output |
| --- | --- | --- | --- | --- | --- | --- |
| W1 | Discovery & Story Session | 1 | 3 hrs | All founders | Company history and origin; the problem and why now; product walkthrough of both apps; current traction and revenue; team; the raise and what it must achieve | Confirmed business understanding; investment thesis draft; consolidated information request list |
| W2 | Financial Modelling — Session 1 | 2 | 3 hrs | Founders + finance lead | Revenue engine and pricing; unit economics — CAC, payback, contribution margin, LTV; cost structure; headcount from the HR plan; the driver tree | Driver tree agreed; assumption book v1 signed off |
| W3 | Financial Modelling — Session 2 | 3 | 3 hrs | Founders + finance lead | Model walkthrough and challenge; use of funds and milestone mapping; valuation method and range; cap table and dilution | Model approved; use of funds agreed; valuation range agreed |
| W4 | Full Data Room Workshop | 4 | 4 hrs | Full leadership team | Data room structure and index walkthrough; every item reviewed; diligence Q&A drill against the investor question bank; gap closure; access control and version discipline | Data room walkthrough complete; readiness sign-off; Phase 1 milestone M2 triggered |
| W5 | Investor Pitch Rehearsal | 5 | 2 hrs | Pitching founders | Live pitch delivery; timing and structure; objection handling drill; the hard questions; follow-up discipline | Pitch calibrated; founders cleared to go live |

B.2 Workshop conduct

Format. In person in Greater Cairo, or remotely by video, at Btakka's preference.

Recording. Sessions are recorded for Btakka's internal use, with consent recorded at the start of each session.

Follow-up. A written summary with decisions, assumptions agreed and action items is issued within two (2) Business Days.

Preparation. A pre-read and preparation list is issued at least two (2) Business Days before each session. Attendees are expected to have reviewed it.

Rescheduling. One reschedule per workshop is permitted on 24 hours' notice. Subsequent reschedules are chargeable under Clause 4.3 of the Consulting Agreement.

Additional sessions. Beyond the five listed, additional workshops may be added by written variation.

Annex C — Client Input Pack

Due: within five (5) Business Days of the Effective Date. The Phase 1 clock starts when the last item is received.

| # | Item | Specification | Received |
| --- | --- | --- | --- |
| 1 | Company profile | Overview, history, key milestones to date, legal structure, ownership, and a plain-language description of what Btakka does | ☐ |
| 2 | HR plan | Current headcount by role and function; current monthly salary cost per role; planned hires with role, seniority, start date and cost; any contractor or agency arrangements | ☐ |
| 3 | Roadmap | 6–12 month product development plan covering both applications, with milestones and target dates | ☐ |
| 4 | App screenshots | High-resolution screenshots of Btakka Business and Btakka Finishing & Decor, covering onboarding and the core user journeys, in PNG or JPG | ☐ |
| 5 | Founding team CVs and photos | Full CV for each founder and key team member; one professional photograph of each, minimum 1000px on the shortest side | ☐ |
| 6 | Brand guidelines | Brand book or style guide; vector logo files (AI, EPS or SVG); colour palette with hex values; typography and font files or names | ☐ |
| 7 | Business model | How Btakka earns revenue today and intends to, across both product lines, including pricing, commission or subscription structure, and any revenue actually collected to date | ☐ |

C.1 Supporting items required from Btakka

Requested formally at Workshop W1 as a single consolidated list, and required within five (5) Business Days of that request:

| Category | Items |
| --- | --- |
| Corporate | Certificate of Incorporation; business registration and licences; founder agreements including vesting; any prior funding instruments (SAFEs, convertible notes, friends-and-family) |
| Financial | Management accounts or financial records for the last 6–12 months; current bank balances; monthly burn; any outstanding liabilities or obligations |
| Traction | App analytics — downloads, installs, activations, active users, retention; transaction or order volume; revenue collected; any cohort data available |
| Customer | Customer or user interviews; reviews and testimonials; pilot or early customer list; any letters of intent |
| Legal | Disclosure of any dispute, claim, regulatory matter, IP issue or contingent liability |
| Optional | Advisor list; key vendor agreements; insurance policies; partnership discussions; customer and advisor references |

End of proposal.

Investment Readiness & Investment Round Management — Proposal

Abdelrhman Soliman · Cairo, Egypt · abdelrhmansoliman96@gmail.com · +20 109 651 5287

Version 1.0 — For Client Review · 13 September 2026 · Document 1 of 2