# INTERNAL — GCC Venture Advisory Bid: Resources, Delivery Plan and KPIs

LEAP Consulting · RFP-VA-2026-09-18 · Not for circulation outside LEAP

This document is for you and your team. It is not part of the submission and must not be sent to Grand Challenges Canada. It covers what we are bidding, what has to be true before we submit, what it takes to deliver if we win, what it earns, and how we will know it is working.

## 1. The deadline

First-phase proposals are due 18 September 2026, 23:59 EST. Today is 15 September 2026. That is three days, and Cairo is 7 hours ahead of Toronto — the deadline falls at 06:59 Cairo time on 19 September, so the practical cut-off for a calm submission is the evening of 18 September Cairo time.

Applications continue on a rolling basis until 18 September 2027, but GCC states it will give preferential selection to first-phase applicants. Submitting late is a materially worse position.

| Milestone | Date | What it means for us |
| --- | --- | --- |
| Proposals due (first phase) | 18 Sep 2026 | Hard target |
| Applicants invited to interview by | 5 Oct 2026 | Interview prep window opens |
| Applicants notified | 19 Oct 2026 |  |
| Contract negotiation | 19 Oct – 20 Nov 2026 | Rates, contract ceiling, reporting, AI policy, GCC frameworks |
| Engagements begin | 1 Jan 2027 | Mobilisation must be complete by 31 Dec 2026 |

Contract runs 1 Jan – 31 Dec 2027, renewable for successive terms of up to two years, to a maximum of six further years. Treat this as a potential seven-year relationship, not a one-year contract. That should govern how we price and how hard we protect delivery quality in year one.

## 2. What we are bidding, and why

### Categories

| Category | Bidding? | Rationale |
| --- | --- | --- |
| 1 — Capital and Financial Strategy | Yes — lead bid | Directly our core practice. 50+ models, 100+ ventures, USD 10M+ supported, data rooms and independent due diligence. Strongest evidence, strongest referees. |
| 2 — Business Models and Operations | Yes — strong | Unit economics and cost structure is the substrate of our modelling work. Credible without stretching. |
| 4 — Market and Policy Navigation | Conditional | Real market-entry and regulatory practice across 5 MENA markets, plus Arabic. Bid only if we can name two real examples with a referee. See §4. |
| 5 — Group-based Learning | Yes | 100+ ventures advised gives us tested curriculum content. Needs cohort-specific evidence — see §4. |
| 3 — Leadership and Organisational Strengthening | No | No referenceable track record in board development, safeguarding, gender or talent strategy. |
| 6 — Specialist Advisory: Evidence, Gender, Environment | No | No monitoring-and-evaluation design or gender-framework track record. |

Bidding 3 or 6 without evidence would fail on the 30% track-record weighting and risks the credibility of the whole submission when GCC calls referees. The RFP and FAQ both confirm categories are scored independently — so a tight four-category bid costs us nothing.

### How the scoring works, and where we win or lose

| Criterion | Weight | Our position | What moves the needle |
| --- | --- | --- | --- |
| Track record | 30% | Weakest link. Real work, but our documented cases are MENA real estate and private ventures, not global-health innovators. | Named examples with quantified before-and-after, and five briefed referees. This is where to spend remaining time. |
| Relevant hands-on expertise and networks | 25% | Strong for 1 and 2; good for 4 within MENA. | Name the associate bench. Depth beats breadth. |
| Fit and approach | 20% | Strong. Our scoping-note / decision-session / close-out-note rhythm matches exactly what GCC describes: time-bound, decision-centric, actionable. | Already built into every outline. |
| Cost | 20% | Structural advantage. Cairo cost base at CAD 123 blended, against Toronto or London providers at two to three times that. | Do not discount further; make the value visible instead. |
| Local contexts | 5% | Good — Arabic named explicitly, and Egypt is an LMIC we operate from, not visit. | Add French or Spanish only with a named associate. |

Our honest win theme: institutional-grade financial and operating analysis, delivered from inside an emerging market, in the innovator’s language, at a cost structure a Toronto firm cannot match.

Our honest risk: no demonstrated global-health or LMIC-innovator portfolio experience. GCC lists primary healthcare, climate and health, and youth mental health as assets, not requirements — but a competitor with equal rigour and sector experience beats us. Mitigations in §4 and §12.

## 3. Submission plan — the next three days

| When | Task | Owner |
| --- | --- | --- |
| Day 1 (15 Sep) | Decide Category 4 in or out. Select and confirm 5 referees — call each, confirm willingness, brief them on which engagement they will be asked about. | Abdelrhman |
| Day 1 | Pull real client examples for Cat 1 (×3), Cat 2 (×3), Cat 5 (×2), Cat 4 (×2 if bidding). Get citation permission where names are used. | Abdelrhman / Ahmed |
| Day 1 | Confirm legal entity details: registered name, form, commercial register no., tax registration. | Abdelrhman |
| Day 2 (16 Sep) | Fill every [[...]] in the five proposal files. Insert real numbers or cut the claim. | Abdelrhman / Ahmed |
| Day 2 | Approve or amend the rate card. Confirm the GST/HST position with the accountant. | Abdelrhman |
| Day 2 | Finalise CVs for every named team member (excluded from page limits — make them substantive). | All named |
| Day 3 (17 Sep) | Page-limit check against §3.1. Proofread. Generate final PDFs. Sign the covering letter. | Abdelrhman |
| Day 3 | Name the associate bench in the general application and Category 4. | Abdelrhman |
| 17–18 Sep | Submit to PortfolioManagement@grandchallenges.ca, subject line “RFP Venture Advisory Support Provider(s)”. Check total attachment size. Request a read receipt or acknowledgement. | Abdelrhman |

Submit a day early. GCC explicitly refuses late proposals for any reason other than its own mishandling — misrouting, traffic, weather and labour disputes are all named as unacceptable excuses.

### Page-limit compliance (§3.1)

| Item | Limit | Measured in the draft | Headroom |
| --- | --- | --- | --- |
| 1. Organisation overview and categories | 1–2 pp | 2 pp | At limit |
| 2. Team members + resumes | No limit on resumes | 2 pp | — |
| 3. Geographic coverage and delivery model | 1–2 pp | 2 pp | At limit |
| 4. Responsible AI approach | 1 p | 1 p | At limit |
| 5. Five references | 1 p | 1 p | At limit |
| 6. Approach — Cat 1 / 2 / 4 / 5 | 3 pp each | 3 / 2 / 2 / 3 | Cat 2 and 4 have room |
| 7. Previous success — Cat 1 / 2 / 4 / 5 | 2–3 pp each | 3 / 2 / 1 / 1 | Cat 1 is at the 3 pp limit |
| 8. Fee structure (per category) | No stated limit | 2–3 pp each | — |

Measured after conversion to Word at 11pt, US Letter, 1 inch margins. Each draft still contains drafting-note blockquotes that you delete before submission — that recovers roughly a third of a page per section, which is your headroom for inserting real examples and referee details. Category 1 item 7 is the exception: it is already at 3 pages with real content, so anything you add there must displace something.

Page numbers include figures and graphics. Resumes and the signed covering letter are excluded. Re-measure after you fill the placeholders — inserted content will push these over.

## 4. Gap register — what must be supplied before we submit

Everything the draft cannot supply, in priority order. Nothing here can be invented.

| # | Gap | Why it matters | Blocking? |
| --- | --- | --- | --- |
| 1 | Five referees, contacted, willing, briefed, tagged by category | 30% weighting, validated by direct call | Yes |
| 2 | Real examples per category with named or agreed-anonymised clients, periods, quantified outcomes | The core of the track-record score | Yes |
| 3 | Legal entity details — registered name, form, register no., tax registration | §2.4 legal capacity; contract cannot be awarded without it | Yes |
| 4 | Signed covering letter referencing RFP-VA-2026-09-18 | §2.1(d): no contract awarded without it; failure to provide on request is disqualifying | Yes |
| 5 | Rate card approval | Ours is a recommendation, not your published rates | Yes |
| 6 | CVs for every named team member | Must evidence hands-on experience in the categories they lead | Yes |
| 7 | Category 4 examples ×2 + referee | If absent, drop Category 4 rather than submit a thin outline | Decision |
| 8 | Category 5 cohort evidence | 1:1 record does not prove cohort delivery | High |
| 9 | Associate bench — names, markets, specialisms | Directly lifts the 25% expertise-and-networks score and the 5% local-contexts score | High |
| 10 | GST/HST position confirmed with accountant | We state a tax position in the fee section | High |
| 11 | Global health / LMIC experience — any at all | Named as an asset in Appendix A | Medium |
| 12 | French or Spanish capability via named associate | Named in Appendix A alongside Arabic | Medium |
| 13 | Third named team member | Two-person core is thin for a multi-category bid | Medium |
| 14 | Named AI tools in the responsible-AI section | FAQ says applicants may wish to include them | Low |

## 5. Resource plan

### Core team and commitment

| Role | Person | Commitment to GCC | Annual hours available | Responsibilities |
| --- | --- | --- | --- | --- |
| Engagement Principal / Account Lead | Abdelrhman Soliman | 35–40% | ~600 | GCC relationship, triage, Cat 1 and 5 lead, final sign-off on all outputs, AI review authority |
| Senior Advisor | Ahmed Ashraf | 30–35% | ~540 | Cat 2 lead, Cat 1 and 4 delivery, model QA |
| Analyst | [[Name / to hire]] | 60% | ~900 | Model build, research, data work, session support |
| Curriculum & Materials Designer | [[Name / associate]] | Per engagement | ~200 | Cat 5 materials, bilingual resource packs |
| Local Associates (Cat 4) | [[Named per market]] | On demand | ~150 total | In-market regulatory and partnership work |
| Coordination / PMO | [[0.2 FTE — can sit with the analyst]] | 20% | ~300 | Scheduling, time tracking, invoicing, KPI dashboard, reference and reporting pack |

Total core capacity available to GCC: approximately 2,400–2,700 hours per year.

### What we need to put in place

| Need | Why | When | Cost estimate |
| --- | --- | --- | --- |
| Analyst capacity (hire or reallocate) | 900 hours is the largest single block; principals cannot absorb it | Before 1 Jan 2027 | [[...]] |
| 2–3 named local associates for Cat 4 | Category is not credible without them | Before submission ideally; before 1 Jan 2027 at the latest | Engaged per assignment |
| Curriculum designer for Cat 5 | 8 modules to build | Nov–Dec 2026 | [[...]] |
| PMO / coordination | Hourly billing needs disciplined time capture, or margin leaks | Nov 2026 | [[...]] |
| Global-health advisory associate | Closes our biggest credibility gap for years 2+ | 2027 | Retained per engagement |

### Concurrency limits

Hard caps, to protect quality:

- Maximum 5 concurrent 1:1 engagements across all categories.

- Maximum 2 concurrent engagements per principal.

- Maximum 1 new cohort module in build at a time, alongside 1:1 work.

- Any assignment that would breach these: we tell GCC the earliest realistic start rather than accept and under-deliver. Saying “not until the 14th” costs one conversation. Missing a deadline in year one of a seven-year relationship costs the relationship.

## 6. Financial model

### Rate card (as proposed — confirm before submission)

| Grade | Rate (CAD/hr) | Notes |
| --- | --- | --- |
| Engagement Principal | 175 | Judgement, client decisions, sign-off |
| Senior Advisor | 130 | Analysis lead |
| Specialist / Curriculum Associate | 95–145 | By discipline |
| Local Associate (Cat 4) | 110 | In-market |
| Analyst | 70 | Build and data work |

Blended rates by category: Cat 1 — 123 · Cat 2 — 121 · Cat 4 — 121 · Cat 5 — priced per session.

### Contract value scenarios

GCC’s total pool is ~CAD 1,300,000 across all providers and categories — not a guarantee to any one applicant. Individual contract ceilings are set at negotiation.

| Scenario | Contract ceiling | Billable hours | Delivery shape |
| --- | --- | --- | --- |
| Conservative | CAD 75,000 | ~610 | ~8 1:1 engagements or equivalent |
| Base case | CAD 150,000 | ~1,230 | ~16 1:1 engagements + a group programme |
| Upside | CAD 250,000 | ~2,050 | ~26 engagements + full cohort programme |

Base case allocation:

| Category | Share | Hours | Engagements |
| --- | --- | --- | --- |
| Cat 1 — Capital and Financial Strategy | 40% | ~490 | 7 engagements averaging 70 hrs |
| Cat 2 — Business Models and Operations | 25% | ~310 | 6 engagements averaging 52 hrs |
| Cat 5 — Group Learning | 25% | ~310 | 5 new modules, 10 repeats, 1 peer exchange, 2 resource packs |
| Cat 4 — Market and Policy Navigation | 10% | ~120 | 3 engagements averaging 40 hrs |

Base case consumes roughly 50% of available core capacity — deliberate. The remaining headroom absorbs over-runs, protects non-GCC work, and leaves room to grow into the upside case without degrading delivery.

### Margin

Replace the cost inputs with your real fully-loaded cost per hour (salary + benefits + allocated overhead ÷ productive hours). The break-even column is what you must stay under:

| Grade | Rate | Break-even cost/hr at 0% margin | Cost/hr for 50% GM | Cost/hr for 65% GM |
| --- | --- | --- | --- | --- |
| Principal | 175 | 175 | 87.50 | 61.25 |
| Senior Advisor | 130 | 130 | 65.00 | 45.50 |
| Local Associate | 110 | 110 | 55.00 | 38.50 |
| Analyst | 70 | 70 | 35.00 | 24.50 |

Target gross margin: 55–65% on a Cairo cost base at these rates. Below 45%, the rate card is wrong or the delivery model is inefficient — investigate rather than absorb.

Three things that destroy margin on this contract, and the control for each:

| Leak | Control |
| --- | --- |
| Hours not captured | Time logged daily against engagement code and grade. Unlogged work is unbilled work. |
| Scope creep inside a fixed-fee package | Hour ceiling in every scoping note; at 80% of ceiling, PMO alerts the principal; anything beyond goes to GCC in writing before it is done. |
| Principal hours on analyst work | Monitor the actual grade mix against the planned blend monthly. A drift to principal-heavy delivery means the blended rate is under-recovered. |

### Payment and currency

- Invoicing monthly in arrears against the contract ceiling, itemised by innovator, engagement, grade.

- [[Confirm at negotiation: payment in CAD to an Egyptian account; who bears FX and transfer cost;   payment terms — push for 30 days.]]

- [[Confirm GST/HST treatment with the accountant, and Egyptian VAT treatment of exported services.]]

## 7. Delivery infrastructure to build before 1 January 2027

| System | Purpose | Build by |
| --- | --- | --- |
| Engagement tracker | One row per engagement: innovator, category, scope, hour ceiling, hours used, dates, status, outcome | Nov 2026 |
| Time capture | Daily logging by engagement and grade. Non-negotiable — it is the invoice, the margin control and the KPI source | Nov 2026 |
| Scoping note template | One page, standard fields, issued within 3 days of triage | Oct 2026 |
| Close-out note template | What changed, decision taken, hours against ceiling, what we would watch, portfolio observation | Oct 2026 |
| Model template library | Standard architecture for the venture model, unit-economics model, cap table, scenario and Monte Carlo layers. Cuts build time 30–40% and makes QA consistent | Nov–Dec 2026 |
| Data room standard | Folder architecture, index, permissions, Q&A tracker | Nov 2026 |
| Cat 5 curriculum | 8 modules: facilitator guide, participant tool, slides, summary — bilingual | Nov–Dec 2026 |
| AI use log | Per engagement: tool, purpose, what it touched, reviewer name | Oct 2026 |
| KPI dashboard | §9 metrics, refreshed monthly | Dec 2026 |
| Follow-up survey instruments | Post-session, 60-day, 3- and 6-month outcome checks | Dec 2026 |
| Secure file transfer | Innovator financial and beneficiary data must never move through consumer channels | Oct 2026 |

## 8. AI governance — standing operating procedure

We have committed to §1.4 D of the RFP in writing. This is how we keep that commitment true.

- Named reviewer per engagement. Recorded in the engagement tracker at scoping. For any quantitative output it is the Principal or the Senior Advisor — no exceptions.

- Enterprise configurations only, with training on inputs disabled and retention controlled. No consumer accounts touch client work.

- Hard prohibition on sensitive data in any uncontrolled tool: innovator financials, cap tables, beneficiary or patient data, unpublished evidence, anything commercially sensitive.

- AI use log per engagement — tool, purpose, what it was applied to, reviewer, date. Disclosable to GCC on request, as we have undertaken.

- Never for findings. AI does not set assumptions, select recommendations, determine valuations or generate figures presented as analysis.

- Associate briefing. Every associate is briefed on this SOP and GCC’s AI policy before starting.

- Opt-out respected. Where GCC or an innovator prefers no AI involvement, we deliver without it and record that in the scoping note.

- Adopt GCC’s policy on award — it is shared at contract negotiation. Review ours against it in November 2026 and reconcile any difference in GCC’s favour.

## 9. KPI framework

Four tiers. Tier C is what GCC actually cares about; Tiers A, B and D are how we keep Tier C possible.

### Tier A — Commercial

| KPI | Target | Cadence |
| --- | --- | --- |
| Contract ceiling drawn down | 85–95% of ceiling by 31 Dec 2027 | Monthly |
| Gross margin on GCC work | 55–65% | Monthly |
| Realisation (hours billed ÷ hours worked) | ≥ 90% | Monthly |
| Utilisation of committed capacity | 45–60% of the 2,400 hrs | Monthly |
| Actual grade mix vs planned blend | Within ±5 percentage points | Monthly |
| Average engagement value | ≥ CAD 6,500 (1:1) | Quarterly |
| Renewal secured for 2028 | Yes | At month 10 |

### Tier B — Delivery discipline

| KPI | Target | Cadence |
| --- | --- | --- |
| Triage call held after assignment | ≤ 5 business days | Per engagement |
| Scoping note issued after triage | ≤ 3 business days | Per engagement |
| Engagements delivered on or before agreed end date | ≥ 95% | Monthly |
| Engagements completed within hour ceiling | ≥ 90% | Monthly |
| Close-out note to GCC after completion | ≤ 5 business days, 100% | Per engagement |
| Revision rounds per deliverable | ≤ 2 | Per engagement |
| Ceiling-breach warnings raised before breach | 100% | Per engagement |
| AI use log completed where AI was used | 100% | Per engagement |

### Tier C — Innovator outcomes

The score that matters. Baseline captured at engagement start so improvement is measured, not asserted.

Category 1 — Capital and Financial Strategy

| KPI | Target |
| --- | --- |
| Decision taken within the engagement window | ≥ 90% |
| Innovator operating their own model unaided at 90 days | ≥ 80% |
| Funder-readiness gaps closed against diligence checklist | ≥ 85% |
| Capital raised following engagement (reported, not claimed) | Tracked at 6 months |
| Runway extension achieved, where that was the objective | Model-verified |

Category 2 — Business Models and Operations

| KPI | Target |
| --- | --- |
| Barrier register produced and prioritised with the innovator | 100% |
| Unit-economics model in use by the innovator at 90 days | ≥ 80% |
| Measurable change in contribution per unit or break-even volume | ≥ 60% of engagements |
| Operating-model decisions taken within window | ≥ 85% |

Category 4 — Market and Policy Navigation

| KPI | Target |
| --- | --- |
| Regulatory pathway documented and verified against primary source | 100% |
| Entry or partnership decision taken within window | ≥ 85% |
| Partner introductions converting to a first meeting | ≥ 60% |
| Registration, licence or procurement milestone progressed at 6 months | Tracked, not guaranteed |

Category 5 — Group Learning

| KPI | Target |
| --- | --- |
| Attendance against enrolment | ≥ 80% |
| In-session tool completed | ≥ 75% |
| Usefulness rating (1–5) | ≥ 4.2 |
| “I will change something”, with the change named | ≥ 70% |
| Change actually made, at 60 days (sampled) | ≥ 50% |
| Cohort completion (3 of 4 sessions) | ≥ 75% |

### Tier D — Relationship

| KPI | Target | Cadence |
| --- | --- | --- |
| GCC Portfolio Manager satisfaction | ≥ 4.5 / 5 | Quarterly |
| Innovator satisfaction | ≥ 4.3 / 5 | Per engagement |
| Innovators who would work with us again | ≥ 85% | Per engagement |
| Portfolio insights surfaced to GCC | ≥ 1 per month | Monthly |
| Assignments declined for capacity | ≤ 10% | Quarterly |
| Escalations to GCC | 0 unresolved | Monthly |

### Attribution discipline

We will be asked to evidence our impact, and Appendix A asks specifically how we attribute it. Standing rule: we report what we contributed and what the innovator decided, separately. A raise that closes after our engagement is reported as “innovator raised X following our support on Y” — never as “we raised X”. Overclaiming survives one reporting cycle and fails the reference check.

## 10. Reporting to GCC

Frequency and format are set at contract negotiation. What we propose:

| Report | Frequency | Contents |
| --- | --- | --- |
| Scoping note | Per engagement | Decision, activities, outputs, hours, dates, innovator inputs |
| Close-out note | Per engagement | What changed, decision taken, hours vs ceiling, what to watch, portfolio observation |
| Monthly report + invoice | Monthly | Engagements active and closed, hours by innovator/engagement/grade, ceiling drawdown, Tier B KPIs, exceptions |
| Quarterly review | Quarterly | Tier C outcomes, portfolio patterns, capacity outlook, proposed curriculum changes |
| Annual report | Month 11 | Full-year outcomes against all tiers, case studies (with innovator permission), renewal proposal |

The monthly exception line matters most: anything at risk goes to GCC before it slips, not in the invoice afterwards.

## 11. Quality assurance

| Control | Applies to | Who |
| --- | --- | --- |
| Scoping note approved before work starts | Every engagement | Principal |
| Model integrity review — assumptions sourced, formulas traced, no hard-coded overrides | Every model | Principal or Senior Advisor, never the builder |
| Peer read before any deliverable leaves | Every deliverable | The other principal |
| AI output review by named qualified reviewer | Where AI used | Principal or Senior Advisor |
| Handover session — innovator can operate the output unaided | Every model or tool | Engagement lead |
| Close-out note reviewed before issue | Every engagement | Principal |
| Ceiling checkpoint at 80% of hours | Every engagement | PMO → Principal |

Escalation: any risk to scope, timeline or quality goes to the Principal same day, and to GCC within 2 business days if it affects what GCC is expecting. We never let GCC learn about a problem from the innovator.

## 12. Risk register

| # | Risk | L | I | Mitigation | Owner |
| --- | --- | --- | --- | --- | --- |
| 1 | Not shortlisted — no global-health track record | M | H | Lead on rigour, cost and Arabic/MENA depth; add any health-adjacent example; engage a global-health associate for renewal years | Abdelrhman |
| 2 | Reference check contradicts a proposal claim | L | Critical | Brief every referee on the specific engagement; no claim in the proposal that a referee cannot confirm | Abdelrhman |
| 3 | Category 4 fails on thin evidence | M | M | Drop the category rather than submit thin; decision at Day 1 | Abdelrhman |
| 4 | Win but under-deliver in year one | L | H | Concurrency caps; decline on capacity rather than over-commit; mobilisation complete before 1 Jan | Abdelrhman |
| 5 | Fixed-fee packages under-priced against real effort | M | M | Hour ceilings; track actual vs estimated per package; re-price at renewal with real data | Ahmed |
| 6 | Key-person dependency — two principals carry the bid | H | H | Build the analyst layer and associate bench; template library reduces principal hours per engagement | Abdelrhman |
| 7 | Contract ceiling set lower than base case | M | M | Prepare a conservative-scenario staffing plan; keep non-GCC pipeline warm | Abdelrhman |
| 8 | Payment, FX or transfer friction Egypt–Canada | M | M | Resolve mechanics at negotiation, in writing, before signature | Abdelrhman |
| 9 | Tax position on GST/HST wrong | L | M | Confirm with accountant before submission; fee section commits to registering if GCC determines otherwise | Abdelrhman |
| 10 | AI commitment breached by an associate | L | H | SOP briefing before any associate starts; AI log audited monthly | Abdelrhman |
| 11 | Innovator data handled insecurely | L | Critical | Secure transfer only; no sensitive data in uncontrolled tools; NDA with every associate | Abdelrhman |
| 12 | Language commitment overstated | L | M | Claim Arabic and English only, unless a named French or Spanish associate is confirmed | Abdelrhman |
| 13 | Conflict — advising an investor and an innovator on the same deal | L | H | Conflict check at triage on every engagement; disclose to GCC before accepting | Abdelrhman |

## 13. Mobilisation plan — award to first engagement

Assumes notification 19 October 2026 and engagements beginning 1 January 2027.

Phase 1 — Negotiation (19 Oct – 20 Nov 2026) Agree contract ceiling and rates. Agree reporting frequency and format. Receive and adopt GCC’s AI policy. Receive GCC’s gender and evidence frameworks if any touch our categories. Agree payment mechanics, currency and FX treatment. Confirm the innovator-matching process and who we deal with day to day. Confirm confidentiality and data-protection terms covering innovator data.

Phase 2 — Build (21 Nov – 20 Dec 2026) Confirm analyst capacity. Sign associate agreements with NDAs and AI SOP briefing. Build the engagement tracker, time capture and KPI dashboard. Finalise scoping and close-out note templates. Build the model template library. Build the first 4 Cat 5 modules. Set up the secure data room standard. Brief the whole team on GCC’s operating model and what “decision-centric and time-bound” means in practice.

Phase 3 — Ready (21–31 Dec 2026) Dry-run a full engagement cycle internally: triage → scoping note → delivery → close-out. Confirm availability calendar for Q1. Agree the first quarter’s cohort curriculum with GCC. Brief GCC on our concurrency caps and escalation route, so expectations are set before the first assignment.

Phase 4 — Live (from 1 Jan 2027) First engagement accepted. First scoping note within 8 business days of assignment. First monthly report to GCC by 5 February 2027.

Review gates: month 3 — delivery discipline (Tier B) holding? · month 6 — outcomes (Tier C) materialising, margin on target? · month 10 — renewal proposal to GCC, backed by a full outcome record.

## 14. Pre-submission checklist

- ☐ Category 4 decision made — in or out

- ☐ Five referees confirmed, briefed, tagged by category

- ☐ Every [[...]] filled or the claim cut — all five proposal files

- ☐ Every quantified outcome verifiable and confirmable by a referee

- ☐ Client permission obtained for every named client

- ☐ Legal entity details complete

- ☐ Rate card approved

- ☐ GST/HST position confirmed with the accountant

- ☐ CVs finalised for every named team member

- ☐ Associate bench named, with markets and specialisms

- ☐ Page limits re-measured after filling — items 1, 3, 4, 5, 6, 7

- ☐ Covering letter signed and referencing RFP-VA-2026-09-18

- ☐ Firm name, contact name, address, telephone and email present (§2.1c)

- ☐ Separate outline and fee proposal per category (§1.4 B)

- ☐ Applicable taxes shown separately in every fee section (§3.1 item 8)

- ☐ Hourly rates shown for all personnel in every fee section

- ☐ No external links or brochures relied on — GCC evaluates only what is submitted (§2.1j)

- ☐ No supporting material beyond what is solicited (FAQ)

- ☐ Files in PDF or Word; total attachment size checked

- ☐ Sent to PortfolioManagement@grandchallenges.ca, subject “RFP Venture Advisory Support Provider(s)”

- ☐ Sent before 18 September 2026, 23:59 EST

- ☐ Acknowledgement of receipt requested

## 15. Interview preparation — start now, not on 5 October

If shortlisted, expect a short interview before final selection. Prepare:

- The strongest single outcome per category, in 90 seconds, with the number and the attribution.

- A straight answer on global health. Do not talk around it: “We have not run a global-health portfolio. What we bring is financial and operating rigour that transfers across sectors, delivered from inside an emerging market in the innovator’s own language. Here is how we would close the sector gap in the first quarter.” Rehearsed honesty beats improvised deflection.

- A worked example of a time-bound, decision-centric engagement — because that phrase is GCC’s own test of fit.

- The capacity answer. How many concurrent engagements, and what happens when they exceed it.

- The AI answer, matching our written SOP exactly.

- Questions for GCC: expected engagement volume by category; how innovators are matched; what past providers got wrong; how GCC defines a successful engagement.